## Task Tracker
Module | Sub-Module | Task | Frontend | FE status | BackEnd | BE status | Planned Date | Development Status | Testing Status | Task Status | Actual Date | Tester | Remarks
Packing | GRN Return | GRN Return Grid View | Dheeraj | Completed | Dheeraj | Completed | 2021-04-12 | Completed | Open | In-Progress | 2021-04-12 | TBD
Packing | GRN Return | GRN Return Detailed View | Dheeraj | Completed | Dheeraj | Completed | 2021-04-03 | Completed | Open | Open | 2021-04-12
Packing | Store Consumption | Store consumption detail view | Dheeraj | Completed | Lakshmi | Completed | 2021-04-03 | Completed | In-Progress | Testing | 2021-04-12 | Sandeep | Could not Test these modules as item master is not fixed
Configuration | Configuration | Layout | Bhanu | Completed | N/A | NA | 2021-03-10 | Completed | Completed | Deployed | 2021-03-26
Masters | Sales |  | Bhanu | Completed | Uma | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26
Masters | Global | Departments | Dheeraj | Completed | Manisha | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Sales | Type of Value Addition4 | Dheeraj | Completed | Uma | Completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Sales | Packing Methods | Dheeraj | Completed | Uma | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Procurement | Items (Pens, Pencils,….) | Dheeraj | Completed | Swathi | Completed | 2021-03-13 | Completed | Open | In-Progress |  | TBD | This task standing as blocker to test other issues developer attention required | NTF
Logistics | Documents -Ready To Process | Plant Invoice | Dheeraj | Completed | yateesh | Open | 2021-04-23 | Open | Open | Open
Logistics | Documents -Ready To Process | Plant Packing List (Dispatch List) | Dheeraj | Completed | yateesh | Open | 2021-04-23 | Open | Open | Open
Logistics | Documents - Inprogress | Container & Sealed List | Dheeraj | Open | yateesh | Open | 2021-04-22 | Hold | Open | Waiting on Client
Logistics | Documents - Inprogress | freigst Invoice | Dheeraj | Completed | Yateesh | Open
Masters | Sales | Brands | Dheeraj | completed | Suraj | Completed | 25-04-2021 | Compleetd
Logistics | Documents - Ready To Ship | Plant Invoice Print | Dileep | completed | Yateesh | Open | 2021-04-24 | Open
Logistics | Documents - Ready To Ship | Plant Packing List | Dileep | completed | Yateesh | Open | 2021-04-23 | Open | Open | Open
Masters | Warehouse | Pallets | Divya | Completed | Nageswar | completed | 2021-04-16 | Completed | Open
Masters | Warehouse | Cells | Divya | Hold | Suraj | Completed | 2021-03-13 | Hold | Hold | Hold |  |  | As per manisha not required
Masters | Warehouse | Columns | Divya | completed | Nageswarao | Completed | 2021-03-13 | Completed | Hold | Hold
Masters | Warehouse | Rack End Customermapping | Divya | Completed | Suraj | Completed | 2021-03-13 | Completed | Hold | Hold
Logistics | Documents - Ready To Ship | Customs invoice | Divya | Open | Yateesh | Open | 2021-04-22 | Open | Open | Open
Logistics | Documents - Ready To Ship | Container & Sealed List | Divya | Hold | Yateesh | Hold | 2021-04-22 | Hold | Open | Waiting on Client
Masters | Global | Grades | Harish | Completed | Suraj | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Sales | Sales | Sale Order Creation & Update | Harish | completed | Uma | completed | 2021-03-22 | Completed | Completed | Closed | 2021-03-26 |  | Uma will complete update by EOD
Packing | GRN Return | GRN Return (Create & Update) | Harish | Completed | Harish | Completed | 2021-04-01 | Completed | Open | In-Progress | 2021-04-12 | TBD | Task need to be completed today as getting delayed since week
Masters | Global | Currencies | Karun karthik | Completed | Suraj | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Sales | Sale Order Types (Rush Order, On PO, Scheduling Agreement, Consignment Fillup, Third-party Order) | Karun karthik | Completed | Swathi | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Sales | Type of Value Addition2 | Karun karthik | Completed | Uma | Completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya | Need Edit access and deactivation access too
Logistics | Documents - Inprogress | Commercial Invoice | Karun karthik | Completed | yateesh | Open | 2021-04-24 | Open | Open | Open
Logistics | Documents - Inprogress | Commercial Packing List | Karun karthik | Completed | yateesh | Open | 2021-04-23 | Open | Open | Open
Logistics | Documents - Inprogress | Shipment Instructions | Karun karthik | Completed | yateesh | Open | 2021-04-23 | Open | Open | Open
Logistics | Documents - Ready To Ship | Commercial Invoice | Karun karthik | completed | Yateesh | Open | 2021-04-23 | Open | Open | Waiting on Client
Logistics | Documents - Ready To Ship | Commercial Packing List | Karun karthik | Completed | Yateesh | Open | 2021-04-22 | Open | Open | Waiting on Client
Logistics | Documents - Ready To Ship | Shipment Instructions | Karun karthik | Hold | Yateesh | Open | 2021-04-23 | Open | Open | Waiting on Client |  |  | No Shipment Instructions in Ready To Ship Submodule
Packing | Bom Calculation | BOM Calculation | Lakshmi | In-Progress | Lakshmi | Completed | 2021-03-30 | Completed | Completed | Closed | 2021-04-05 |  | will be completed by 9.00pm/Detail view need to be done
Packing | Store Returns | Store Returns (Create) | Lakshmi | Dev Completed | Manisha | Completed | 2021-04-01 | Completed | In-Progress | Testing | 2021-04-07 | Sandeep | Could not Test these modules as item master is not fixed
Packing | Store Returns | Store returns Grid View | Lakshmi | Completed | Manisha | Completed | 2021-04-02 | Completed | In-Progress | Testing | 2021-04-07 | Sandeep | Could not Test these modules as item master is not fixed
Packing | Store Returns | Store returns detailed View | Lakshmi | Completed | Manisha | Completed | 2021-04-03 | Completed | In-Progress | Testing | 2021-04-07 | Sandeep | Could not Test these modules as item master is not fixed
Masters | Vendors | Vendors | Lakshmi | Completed | Lakshmi | Completed | 2021-04-10 | Completed | Open | In-Progress | 2021-04-12 | TBD | As per developer development will be completed within day
Packing | Bom Calculation | System calculated BOM Calculation (Change Request) | Lakshmi | Completed | Lakshmi | Completed | 2021-04-13 | Completed | Open | Open
Logistics | Container Register | Screen to update the status as Slot Booked | Lakshmi | Completed | Lakshmi | Completed | 2021-04-17 | Completed | Open | Open
Logistics | Container Register | Screen to update the status as Dispatched To Plant once container reached to Plant | Lakshmi | Completed | Lakshmi | Completed | 2021-04-17 | Completed | Open | Open
Logistics | Documents -Ready To Process | Code List & PO Download | Lakshmi | Open | yateesh | Open | 2021-04-22 | Open | Open | Open
Logistics | Documents - Doc Head Approval | 1st level Approval screen with above list of items (Ready to Ship) check list | Lakshmi | Open | Yateesh | Open | 2021-04-26 | Open | Open | Open
Logistics | Documents - Logistics Head Approval | 2nd level Approval screen with above list of items (Ready to Ship) check list | Lakshmi | Open | Yateesh | Open | 2021-04-26 | Open | Open | Open
Masters | Logistics | Vehicle Master | Manisha | Open | Manisha | Completed | 2021-03-13 | Open | Open | Hold
Masters | Warehouse | Zone master | Manisha | Completed | Manisha | Completed | 2021-03-13 | Completed | Hold | Hold
Masters | Warehouse | Racks | Manisha | Completed | Suraj | Completed | 2021-03-13 | Completed | Hold | Hold
Masters | Warehouse | Level | Manisha | completed | Suraj | Completed | 2021-03-13 | Completed | Hold | Hold
Sales | Sales | Sale Order Tracking | Manisha | Completed | Manisha | Completed | 2021-03-22 | Completed | Completed | Closed | 2021-03-26
Packing | SO Tracker | So Tracker dashboard for packing material requisition | Manisha | completed | Uma | Completed | 2021-03-30 | Completed | Open | In-Progress | 2021-04-12 |  | Code need to be pushed
Packing | Store Consumption | Store Consumption (Create) | Manisha | Completed | Lakshmi | Completed | 2021-04-01 | Completed | In-Progress | Testing | 2021-04-12 | Sandeep | Could not Test these modules as item master is not fixed
Packing | Store Consumption | Store consumption grid view | Manisha | Completed | Lakshmi | Completed | 2021-04-02 | Completed | In-Progress | Testing | 2021-04-12 | Sandeep | Could not Test these modules as item master is not fixed
Ware House | Stock In - GUN - FG Report - API | Sale order numbers and respective Sale order items which have Open & In-progress status | NA | NA | Manisha | Completed | 2021-04-25 | Completed | Open | hold | TBD | TBD | Kept on hold as requiremnt is not clear
Ware House | Stock In - GUN - FG Report - API | Receive report quantity against to so item and return suggested Pallet Type & Location | NA | NA | Manisha | Completed | 2021-04-27 | Completed
Ware House | Stock In - GUN - FG Report - API | If pallet type is new accept pallet number, assign location & raise Fork Lift job | NA | NA | Satish | Open | 2021-04-28 | Open
Ware House | Stock In - GUN - FG Report - API | If pallet type is Old, Receive pallet number, sale order, sale order item, report quantity & Update stock | NA | NA | Satish | Open | 2021-04-28 | Open
Ware House | Stock in - Forklift - API | If user selects Existing Pallet raise a fork lift job(pallet number, location) with type refill | NA | NA | Satish | Open | 2021-04-28 | Open
Ware House | Stock In - GUN - FG Report - API | Receive pallet number,report quantity & update the stock against to existing location & pallet number | NA | NA | Satish | Open | 2021-04-28 | Open
Ware House | Stock in - Forklift - API | Receive pallet number, location, scan status, time stamp & update stock status | NA | NA | Satish | Open | 2021-04-29 | Open
Ware House | Stock in - Forklift - API | Fork lift job completion acknowledgement | NA | NA | Satish | Open | 2021-04-29 | Open
Ware House | Stock In | Update Slot status as Ready to Book, Doc Status as IN progress when SO qnty reached to 75% | NA | NA | Satish | Open | 2021-04-29 | Open
Ware House | Stock Out | Fork lift job to dispatch the FG with Stockout status contains Sale order number, location & pallet numbers | NA | NA | Satish | Open | 2021-04-29 | Open
Logistics | Documents - Ready To Ship | Insurance(Upload) | Nageswarao | completed | Nageswarao | In-Progress | 2021-04-23 | Open | Open | Waiting on Client
Logistics | Documents - Ready To Ship | Bank copy | Nageswarao | Hold | Nageswarao | Open | 2021-04-24 | Open | Open | Waiting on Client
Masters | Global | UOMs | Niveditha | Completed | Manisha | Completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Sales | Type of Food | Niveditha | Completed | Uma | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Warehouse | Locations | Niveditha | completed | Nageswarao | Completed | 2021-03-13 | Completed | Hold | Hold
Logistics | Documents - Ready To Ship | Plant Invoice Grid view | Niveditha | Completed | Yateesh | Completed | 2021-04-22 | Open
Logistics | Documents - Ready To Ship | Plant Invoice Detailed View | Niveditha | Open | Yateesh | Completed | 2021-04-23 | Open
Masters | Global | Taxes | Pavan | Completed | Manisha | Completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Global | Vendors | Pavan | Completed | Suraj | completed | 2021-03-13 | Completed | Completed | Closed | 2021-04-09 | Sowjanya
Masters | Sales | Type of Value Addition1 | Pavan | Completed | Uma | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya | Need Edit access and deactivation access too
Masters | Sales | BOM Yielding Parameters (Soaking, Glazzing...) | Pavan | Hold | Suraj | Hold | 2021-03-13 | Hold | Hold | Hold
Masters | Sales | Destination | Pavan | Completed | Bugs raised in testing | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya | Bugs raised in testing
Masters | Sales | End customers | Pavan | Completed | Swathi | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya | Bugs raised in testing
Masters | Sales | Sales person | Pavan | Not Required | Swathi | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Procurement | Item Damage Reasons | Pavan | Completed | Uma | Completed | 2021-03-29 | Completed | Completed | Closed | 2021-04-10
Packing | GRN | GRN Detailed View | Pavan | Completed | Uma | Completed | 2021-04-02 | Completed | Completed | Testing | 2021-04-12
Configuration | Configuration | Configuration | RK | Completed | RK | NA | 2021-03-10 | Completed | Completed | Deployed | 2021-03-26
Configuration | Functional | Define Masters | RK | Completed | N/A | NA | 2021-03-10 | Completed | Completed | Deployed | 2021-03-26
Logistics | Documents - Ready To Ship | CNF Status | Rohit | Hold | Yateesh | Open | 2021-04-22 | Open | Open | Waiting on Client
Logistics | Documents - Ready To Ship | ISF Worksheet(USA) | Rohit | Open | Yateesh | Open | 2021-04-23 | Open | Open | Waiting on Client
Masters | Global | Countries | sharat | Completed | Suraj | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Global | Payment modes | Sharat | Completed | Swathi | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Global | Certificates | sharat | Completed | Swathi | Completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Sales |  | Suraj | Completed | Manisha | Completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26
Masters | Procurement | Procurement Status | Suraj | Hold | Suraj | Hold | 2021-03-13 | Hold | Open | Open
Sales | Sales | Sale Order Grid View & excel export | Suraj | Completed | Suraj | Completed | 2021-03-22 | Completed | Completed | Closed | 2021-03-26 |  | code pushed to live
Packing | Purchase Order | Purchase Order (Create & Update) | Suraj | Completed | Swathi | Completed | 2021-04-02 | Completed | Hold | Hold | 2021-04-07
Packing | Purchase Order | Purchase order approval | Suraj | Completed | Swathi | Completed | 2021-04-03 | Completed | In-Progress | Testing | 2021-04-05 | Sandeep | Could not Test these modules as item master is not fixed
Packing | Purchase Order | Purchase Order Grid view | Suraj | Completed | Swathi | Completed | 2021-04-03 | Completed | In-Progress | Closed | 2021-04-05 | Sandeep | Could not Test these modules as item master is not fixed
Packing | GRN | Stock Management | Suraj | Completed | Yateesh | Completed | 2021-04-03 | Completed | Hold | Hold |  |  | Create completed Updation left/on hold as dev doing SO
Packing | GRN | Stock Grid | Suraj | Completed | Uma | Completed | 26-04-2021 | Completed
Packing | Purchase Order | SO based auto generated PO (Change Request) | Suraj | Completed | Lakshmi | Completed | 2021-04-12 | Completed | Open | In-Progress | 2021-04-13 | TBD | Create will be completed by 12 and update will be completed by 13th april
Dashboard | Factory Head Dashboard | Sale Orders status wise Tab View | Suraj | Completed | Suraj | Completed | 2021-04-17 | Completed |  | Open
Dashboard | Factory Head Dashboard | Re-packing Inventory - suggestion | Suraj | Open | Suraj | Open | 2021-04-22 | Open |  |  |  |  | Delayed due to having dependancy with warehouse
Dashboard | Factory Head Dashboard | Re-processing Inventory | Suraj | Open | Suraj | Open | 2021-04-22 | Open |  |  |  |  | Delayed due to having dependancy with warehouse
Logistics | Container Register | Container register in tab view (based on slot status) | Suraj | Completed | Suraj | Completed | 2021-04-17 | Completed | Open | Open | 2021-04-19
Logistics | Container Register | Screen to assign/change the SO for the container | Suraj | Completed | Lakshmi | Completed | 2021-04-19 | Completed | Open | Open | 2021-04-21
Logistics | Container Register | Screen to change the loading status and fill Loaded, Sealed Info & Change the documentation status as Inprogress | Suraj | Completed | Laxmi | Completed | 2021-04-19 | Completed | Open | Open
Logistics | Container Register | Screen to change the status as Shipped | Suraj | Completed | Laxmi | Completed | 2021-04-19 | Completed | Open | Open
Logistics | Bill Of Lading | Grid view for Bill of Lading (status wise tab view) | Suraj | Completed | Laxmi | Completed | 2021-04-19 | Completed | Open | Open
Logistics | Bill Of Lading | Screen to change the status as Draft Received | Suraj | Completed | Laxmi | Completed | 2021-04-20 | Completed | Open | Open
Logistics | Bill Of Lading | Screen to change the status as OBL Received | Suraj | Completed | Laxmi | Completed | 2021-04-20 | Completed | Open | Open
Logistics | Bill Of Lading | Screen to change the status as Received and Shared & Close the SO | Suraj | Completed | Suraj | In-Progress | 2021-04-20 | In-Progress | Open | Open
Logistics | Documents -Ready To Process | Customs invoice | Suraj | Completed | yateesh | In-Progress | 2021-04-22 | In-Progress | Open | Open
Ware House | Ware house Dashboard | Total Warehouse Capacity | Suraj | In-Progress | Manisha | Open | 2021-05-02 | In-Progress
Ware House | Ware house Dashboard | Zone wise warehouse capacity | Suraj | In-Progress | Manisha | Open | 2021-05-02 | In-Progress
Ware House | Ware house Dashboard | Rackwise Filled Vs Partially Filled Vs Availability | Suraj | In-Progress | Manisha | Open | 2021-05-02 | In-Progress
Ware House | Ware house Dashboard | Planned dispatches for the next 15,30,45 days | Suraj | In-Progress | Manisha | Open | 2021-05-02 | In-Progress
Ware House | Ware house Dashboard | Planned occupancy for the next 15,30,15 days | Suraj | In-Progress | Manisha | Open | 2021-05-02 | In-Progress
Ware House | Stock Report | Sale order wise Summarized and detailed stock with aging | Suraj | Open | Manisha | Open | 2021-05-02 | Open
Ware House | Fork list Jobs | Fork lift jobs with status | Suraj | Open | Manisha | Open | 2021-05-02 | Open
Packing | Purchase Order | Purchase order Detailed View & print | Swathi | In-Progress | Swathi | Completed | 2021-04-01 | Completed | In-Progress | Testing | 2021-04-12 | Sandeep | Could not Test these modules as item master is not fixed
Packing | GRN | Goods Received Note (GRN) create | Uma | Completed | Uma | Completed | 2021-04-02 | Completed | In-Progress | Testing | 2021-04-12 | Sandeep | Could not Test these modules as item master is not fixed
Packing | GRN | Goods Received Note (GRN) update | Uma | Hold | Uma | Hold |  | Hold
Packing | GRN | GRN Grid view | Uma | Completed | Uma | Completed | 2021-04-03 | Completed | Completed | Testing | 2021-04-12
Sales | Sales Order | System should calculate required BOM | Uma | Completed | Uma | Completed | 2021-04-12 | Completed |  | In-Progress | 2021-04-12 |  | As per developer will be completed with in day
Logistics | Documents - Ready To Ship | Plant Invoice creation | Uma | Completed | Lakshmi | In-Progress | 2021-04-20 | Open | Open | Open
Logistics | Documents - Ready To Ship | Plant Invoice Update | Uma | In-Progress | Lakshmi | Open | 2021-04-22 | Open
Masters | Global | Customers | Venkatesh | Completed | Manisha | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya | Bugs raised in testing
Masters | Global | HRMS-employee_details | Venkatesh | Completed | Swathi | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Sales | Sale Process type (MTO, MTS) | Venkatesh | Completed | Swathi | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26
Masters | Sales | Type of Value Addition3 | Venkatesh | Completed | Uma | Completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya | Need Edit access and deactivation access too
Masters | Sales | Shipping Terms | Venkatesh | Completed | Swathi | completed | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 | Sowjanya
Masters | Procurement | Item Categories (Stationary, Computers,Furniture, Chemicals) | Venkatesh | Completed | Uma | completed | 2021-03-13 | Completed | Completed | Closed |  | Sowjanya
Masters | Procurement | GRN Rejection Reasons | Venkatesh | Completed | Uma | Completed | 2021-03-29 | Completed | Completed | Closed | 2021-04-02
Masters | Sales | Sales_life Cycle |  | N/A | Swathi | N/A | 2021-03-13 | Completed | Completed | Closed | 2021-03-26 |  | Code doesn't exist
Ware House | Pallets Report | Pallets status Report |  | Open | Manisha | Open |  | Open
Ware House | Locations Report | Locations Status Report |  | Open | Manisha | Open
Masters | Raw Material | Maintain HL wastage %
Masters | Raw Material | Supplier category (Raw Material/ Packing Material)
Masters | Raw Material | Supplier Type (Agent/Broker/ Farmer/ material)
Masters | Raw Material | Farmers & Farm Codes
Masters | Raw Material | Hatcheries
Raw Material | BOM Calculation | Raw Material BOM Calculation on Sale order Save
Raw Material | BOM Calculation | BOM Calculation Grid View (Tab)
Raw Material | Factory Head Dashboard | Assign Repacking material to Sale order
Raw Material | Factory Head Dashboard | Assign Re-processing material to Sale order
Raw Material | RM Procurement Dashboard | Summarized info on Raw Material Required with filters
Raw Material | Indent | Indent Creation
Raw Material | Indent | Indent Update
Raw Material | Indent | Indent Grid View
Raw Material | Indent | Indent Detailed View
Raw Material | GRN | GRN Creation
Raw Material | GRN | GRN Update
Raw Material | GRN | Assign Sale order number for GRN
Raw Material | BOM Calculation | Update BOM requirement after FG Reporting
User Management | Passport | Passport-jwt module
User Management | Authentication | Maintain Auth module
User Management | User | Maintain User Module
User Management | User | Calling services from employees masters
User Management | User | Session Handling
User Management | User | Login Screen
User Management | User | Define User roles to respective menus and screens

## Questions
S.No | Question
1 | GRN Retuns
2 | Minimum Stock
3 | Transportation Cost item wise or for total Items
4 | Forklist Job Cancellation Reasons required or not(within 3 hrs)

## Bug Sheet
S.No | Module | Sub module | Task | Bug Description | Issue | Category | Raised by | Raised Date | Dev Status | Testing Status | Assignee | Resolved Date | Remarks
1 | Masters | Sales | SKU code |  | Bug | Sql Error | Sowjanya | 2021-03-27 | Completed | Pass |  | 2021-04-01
2 | Masters | Procurement | Vendors | 1. In vendors Deactivate/Activate pop message displays wrong | Bug | UI | Sowjanya | 2021-03-27 | Completed | Pass |  | 2021-04-01
3 | Masters | Sales | End Customer | 1.Unable to add end customer details getting error as ER_TRUNCATED_WRONG_VALUE_FOR_FIELD: Incorrect integer value: 'USR' for column 'currency_id' at row 1 | Bug | Sql Error | Sowjanya | 2021-04-02 | Completed | Pass | Suraj
4 | Masters | Procurement | Items | 1.Unable to add Items getting error as ER_NO_DEFAULT_FOR_FIELD: Field 'created_user' doesn't have a default value | Bug | Sql Error | Sowjanya | 2021-04-03 | Completed | Pass | harish
5 | Masters | Sales | End Customer | End customers form does not accept Preloaded currencies (shows integer error) | Bug | Functional | Leo | 2021-04-03 | Completed | Pass | harish
6 | Masters | Sales | Destination | Cannot give long value characters | Bug | Validation | Leo | 2021-04-03 | Completed | Pass | Uma
7 | Masters | Sales | SKU Codes | Replace "STTP" with "STPP" | Bug | UI | Leo | 2021-04-05 | Completed | Pass | harish
8 | Masters | Sales | End Customer | 1.Name of end customer character limit need to increase 2.Issue in end customer updation form(Updated in descending order) | Bug | Validation | Sowjanya | 2021-04-06 | Completed | Pass | Harish
9 | Masters | Sales | SO Tracker | "Item details" units are showing wrong for 1.Pack type 2.Case weight 3. Net weight | Bug | Functional | Sowjanya | 2021-04-06 | Completed | Pass | manisha |  | bug resolved, code pushed
10 | Masters | Sales | SO Creation - Product Details | Should not allow negative values for Soaking time, unit price, No of cases | Bug | Validation | Sandeep | 2021-04-06 | Completed | Pass | Uma
11 | Masters | Sales | SO Creation | Double click on Submit button 2 records are inserted.should disale the button on single click | Bug | Functional | Sandeep | 2021-04-06 | Completed | Pass | Uma
12 | Masters | Sales | SO Creation | in Category, rename "Screw" to "Skewers" | Bug | UI | Leo | 2021-04-06 | Completed | Pass | Uma
13 | Masters | Sales | So view | 1. In sale order tracker unable to view SO details getting error as Request failed with status code 404 | Bug | Functional | Sowjanya | 2021-04-05 | Completed | Pass | Manisha | 2021-04-05
14 | Masters | Global | Customers | 1.Country name displays wrong in customers view 2.Currency name dislays wrong in customers view 3.Payment mode displays wrong in customers view | Bug | Functional | Sowjanya | 2021-04-03 | Completed | Pass | harish |  | Harish need to give time lines
15 | Masters | Sales | SO Creation | UOM is faulty for "Case weight" and "Net Weight". - should show in "LB's" for either pound or lb itself (Automatic Conversion) -show show in "KG's" for either grams or KG's itself (Automatic Conversion) | Bug | Functional | Leo | 2021-04-06 | Completed | Pass | Uma |  | not a bug,requirement
16 | Masters | Sales | SO Creation | Total pouches counting is wrong ( no. of pouches per carton multiplied to no of cartons. ) | Bug | Functional | Leo | 2021-04-06 | Completed | Pass | Uma
17 | Masters | Sales | SO Creation |  | Bug |  | Leo | 2021-04-06 | Completed | Pass | Bhanu
18 | Masters | Sales | SO Creation | In Product Details, Net Amount should not show decimal values, it should round off to the closest value of that number. Currently it shows more than 8 decimal numbers | Bug | Validation | Leo | 2021-04-07 | Completed | Pass | uma
19 | Masters | Procurement | Item category | 1.item category form, vendors and items are duplicated. 2. item category view form , R should be captail for Remarks column | Bug | UI | Sandeep | 2021-04-08 | Completed | Pass | Dileep
20 | Masters | Procurement | Sizes | Size column not accepting integer values | Bug | Validation | Sandeep | 2021-04-08 | Completed | Pass | Niveditha
21 | Masters | Sales | SO detail view | Rename " Load Inpection" to " Load Inspection" | Bug | UI | Leo | 2021-04-09 | Completed | Pass | Manisha
22 | Masters | Sales | SO Creation | The Second product details if edited and updated, is replicating the first product details than the given updates | Bug | Functional | Leo | 2021-04-09 | Completed | Pass | Uma
23 | Masters | Sales | Destination | Destination Names wont update | Bug | Functional | Leo | 2021-04-09 | Completed | Pass | Niveditha
24 | Masters | Procurement | Items, vendors | Create forms showing 2times and unable to create due to net work error | Bug | Functional | Sandeep | 2021-04-12 | Completed | Pass
25 | Masters | Procurement | ITEMS | In updation form product code name renamed as item code | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Dileep
26 | Masters | Global | Departments | Total Departments: should be left alignment | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Niveditha | 2021-04-14
27 | Masters | Global | Tax | Tax % should not accpet negative values | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Niveditha
28 | Masters | Global | Tax | Missing Sorting feature | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Niveditha | 2021-04-14
29 | Masters | Global | Currency | Currency name should be unique | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Niveditha |  | Fixed but not tested, please confirm after testing.
30 | Masters | Global | Currency | Currency name search not working | Bug | Functional | Sandeep | 2021-04-14 | Completed | Pass | Niveditha | 2021-04-14
31 | Masters | Global | Currency | Click on sorting it is showing blank page | Bug | Functional | Sandeep | 2021-04-14 | Completed | Pass | Niveditha | 2021-04-14
32 | Masters | Global | Employee | Employee update is showing error 'ER_DUP_ENTRY: Duplicate entry | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Niveditha
33 | Masters | Global | Employee | Mobile number should accept Integer values and provide validation | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Niveditha
34 | Masters | Global | Employee | Click on sorting it is showing blank page | Bug | Functional | Sandeep | 2021-04-14 | Completed | Pass | Niveditha
35 | Masters | Global | Customers | Mobile number should accept numeric values | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
36 | Masters | Global | Customers | Provide proper validion message for required field for address | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
37 | Masters | Global | Customers | Click on sorting it is showing blank page | Bug | Functional | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
38 | Masters | Global | Customers | With out filling first line addressshould not allow for add address | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Niveditha |  | Update happens only when input values are given.
39 | Masters | Global | Customers | What is address line 1 and 2 | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
40 | Masters | Global | Countries | Click on sorting it is showing blank page | Bug | Functional | Sandeep | 2021-04-14 | Completed | Pass | Niveditha | 2021-04-14
41 | Masters | Global | Countries | Country name text field should be left alignmnet | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Niveditha
42 | Masters | Global | Certifications | Remarks column name R should be captail |  | UI | Sandeep | 2021-04-14 | Completed | Pass | Niveditha | 2021-04-14
43 | Masters | Global | Packing methods | In Add it is packing method name but in view it is showing packing service name should follow same in both create and view | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Niveditha | 2021-04-14
44 | Masters | Global | Packing methods | Pouches per row and no of pouches should not accpet negative values and provide valid alert message if user enter negative values | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Niveditha
45 | Masters | Global | Delivery terms | Enter space bar and click on submit delivery terms are saved | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Niveditha
46 | Masters | Global | Delivery terms | Remove cancel button in update form | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Karun Karthik
47 | Masters | Global | Delivery terms | Change the Total column name into Total delivery terms | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Karun Karthik
48 | Masters | Global | shipping term name | Enter space bar and click on submit delivery terms are saved | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Karun Karthik
49 | Masters | Global | shipping term name | Remove cancel button in update form | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Karun Karthik
50 | Masters | Global | shipping term name | Change the Total column name into Total shipping term name | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Karun Karthik
51 | Masters | Sales | Products | Enter space bar and click on submit products are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
52 | Masters | Sales | Food type | Enter space bar and click on submit SO types are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
53 | Masters | Sales | SO process types | Change the label name as Sale Order Process Types instead of Sale order process details in header | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
54 | Masters | Sales | Food type | Enter space bar and click on submit Food type data are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
55 | Masters | Sales | Food type | Change the label name as Food Type instead of type of food in header | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
56 | Masters | Sales | Value Addition 1 | In create page total type of value addition 1 name and count displays wrong | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
57 | Masters | Sales | Value Addition 1 | Enter space bar and click on submit value addition 1 details are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
58 | Masters | Sales | Value Addition 2 | In create page total type of value addition 2 name and count displays wrong | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
59 | Masters | Sales | Value Addition 2 | Enter space bar and click on submit value addition 2 details are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
60 | Masters | Sales | Value Addition 3 | In create page total type of value addition 3 name and count displays wrong | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
61 | Masters | Sales | Value Addition 3 | Enter space bar and click on submit value addition 3 details are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
62 | Masters | Sales | Value Addition 3 | Change the label name as Type Of Value Addition Three instead of Types Of Value Addition Three in header | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass
63 | Masters | Sales | Value Addition 4 | Enter space bar and click on submit value addition 4 details are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
64 | Masters | Sales | Value Addition 5 | Enter space bar and click on submit value addition 5 details are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
65 | Masters | Sales | Destination | In create page Total renamed as Total destinations | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
66 | Masters | Sales | Destination | Enter space bar and click on submit destination data are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
67 | Masters | Sales | End customer | In create page total end customer count displays wrong | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
68 | Masters | Sales | End customer | Duplicates are allowed | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass
69 | Masters | Sales | End customer | Enter space bar and click on submit end customer details are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
70 | Masters | Sales | SKU code | View button is missing in SKU Code | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Dileep
71 | Masters | Sales | SKU code | Enter space bar and click on submit SKU code details are saved | Bug | Validation | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
72 | Masters | Sales | Roles | Unable to add roles getting error as Request failed with status code 404 | Bug | Functional | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
73 | Masters | Procurement | Item category | Enter space bar in item category and click on save item category is saved | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
74 | Masters | Procurement | Item category | Change the total column name into Total item category | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Dheeraj
75 | Masters | Procurement | Vendors | Gst lable name should be GST | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
76 | Masters | Procurement | Vendors | Provide validation for mandatory fileds for both add and update forms | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
77 | Masters | Procurement | Vendors | Unable to sort vendor name | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass
78 | Masters | Procurement | Vendors | Total vendors and should be left alignment | Bug | UI | Sowjanya | 2021-04-14 | Completed | Pass | Karun Karthik
79 | Masters | Procurement | GRN Rejection reasons | 1.Click on sorting it is showing blank page 2.unable create GRN rejection reasons | Bug | Functional | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
80 | Masters | Procurement | Sizes | Unable to add sizes showing enter only alphabets. | Bug | Validation | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
81 | Masters | Procurement | Items, Vendors | Create forms showing 2times | Bug | UI | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
82 | Masters | Global | Taxes | in taxes form rename Tax% lable as Tax Percentage(%) | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
83 | Masters | Global | Taxes | View button missing in Update taxes | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
84 | Masters | Global | Taxes | in taxes view change the apeend % symbol to tac percentage ,lable should br Tax Percentage(%) | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
85 | Masters | Global | Departments | in update view button not working, | Bug | Functional | Swathi | 2021-04-14 | Completed | Pass | Karun Karthik
86 | Masters | Global | Currency | in update view button not working, | Bug | Functional | Swathi | 2021-04-14 | Completed | Pass | Karun Karthik
87 | Masters | Global | In all grids | If view button not working in update remove the button | Suggesition | UI | Swathi | 2021-04-14 | Completed | Pass | Karun Karthik
88 | Masters | Global | Payment Modes | Change the menu name as Payment Modes instead of Payment modes | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
89 | Masters | Global | Payment Modes | Change the lable name as Payment Mode instead of Payment modes in form | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
90 | Masters | Global | Payment Modes | Change the lable name as Payment Modes instead of Payment modes in grid | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
91 | Masters | Global | Payment Modes | Change the lable name as Payment Modes instead of Payment modes in header | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
92 | Masters | Global | Employees | Change the menu name as Employees instead of Employee | Bug | UI | Swathi | 2021-04-14 | Completed | Reopen | Dheeraj
93 | Masters | Global | Employees | Sorting Missing for roles | Bug | UI | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
94 | Masters | Global | Customers | Change client name into customer name in customer detai form and grid view |  | UI | Sandeep | 2021-04-15 | Completed | Pass | Dheeraj
95 | Masters | Global | Country | Country name should not accept numeric values | Bug | Validation | Sandeep | 2021-04-15 | Completed | Pass | Dheeraj
96 | Masters | Procurement | Vendors | In create page total renamed as Total Vendors | Bug | UI | Sowjanya | 2021-04-15 | Completed | Pass
97 | Masters | Procurement | Item Category | In create page total renamed as Total Item Categories | Bug | UI | Sowjanya | 2021-04-15 | Completed | Pass | Dheeraj
98 | Masters | Procurement | GRN Rejection reasons | In create page total renamed as Total GRN Rejection Reasons | Bug | UI | Sowjanya | 2021-04-15 | Completed | Pass | Dheeraj
99 | Masters | Global | Payment terms | In create page total payment terms displays wrong | Bug | Functional | Sowjanya | 2021-04-16 | Completed | Pass | Niveditha
100 | Masters | Global | Payment terms | In create page total sale persons name renamed as Total Payment Terms | Bug | UI | Sowjanya | 2021-04-16 | Completed | Pass | Niveditha
101 | Masters | Global | Packing Methods | Change the PouchesWeight into Pouches Weight in packing Methods form | Bug | Lable change | Sandeep | 2021-04-19 | Completed | Pass | Niveditha
102 | Masters | Global | Packing Terms | Change the Menu name as Packing terms into Packing Terms | Bug | Lable change | Sandeep | 2021-04-19 | Completed | Pass | Niveditha
103 | Masters | Global | Delivery terms | Change the Menu name as Delivery terms into Delivery Terms | Bug | Lable change | Sandeep | 2021-04-19 | Completed | Pass | Niveditha
104 | Masters | Global | Shipping terms | Change the Menu name as Shipping terms into Shipping Terms | Bug | Lable change | Sandeep | 2021-04-19 | Completed | Pass | Niveditha
105 | Packaging | PO | PO | Saleorder dropdown is empty | Bug | Functional | Sowjanya | 2021-04-05 | Completed | Pass | Suraj
106 | Packaging | Store Issues | Store consumption | Store consumption form in not working | Bug | Functional | Sowjanya | 2021-04-05 | Completed | Pass | Manisha | 2021-04-26 | bug resolved, code pushed
107 | Packaging | BOM Calculation | BOM Calculation | Quantity should not allow negative values | Bug | Validation | Sandeep | 2021-04-08 | Completed | Pass | lakshmi | 2021-04-08
108 | Packaging | GRN | GRN | Change the Total into Total GRN s in GRN details form | Bug | UI | Sandeep | 2021-04-15 | Completed | Pass | Dheeraj
109 | Packaging | GRN | GRN | Change the Grn name into GRN Name, and Grn date into GRN Date | Bug | UI | Sandeep | 2021-04-15 | Completed | Pass | Dheeraj
110 | Packaging | GRN | GRN Return | Change column names as GRN Number ,GRN Return Date and GRN Return Number | Bug | UI | Sandeep | 2021-04-15 | Completed | Pass | Dheeraj
111 | Packaging | BOM calculation | BOM Details | Search and sorting options are overlapped for Custmer name and end custmer name | Bug | UI | Sandeep | 2021-04-15 | Completed | Reopen | Dileep
112 | Packaging | BOM calculation | BOM Details | Search and sorting option is missing for ETA and ETD | Bug | UI | Sandeep | 2021-04-15 | Completed | Pass | Niveditha
113 | Packaging | GRN | GRN Details | Change the text field name as total Cost into Total Cost | Bug | UI | Sandeep | 2021-04-17 | Completed | Pass | dileep
114 | Sales | SO Creation | Product Details | 1. Unable to add product details in SO Creation getting errror as ER_BAD_FIELD_ERROR: Unknown column 'sku_codes.value_addition_four_id' in 'field list' | Bug | Sql Error | Sowjanya | 2021-03-29 | Completed | Pass |  | 2021-04-01
115 | Sales | SO Creation | Product Details | Replace "Glazzing" with "Glazing" | Bug | Spell error | Leo | 2021-03-27 | Completed | Pass
116 | Sales | SO Creation | Product Details | Replace "Varient" with "Variant" | Bug | Spell error | Leo | 2021-03-27 | Completed | Pass
117 | Sales | SO Creation | Product Details | Replace "Style Weightment" with "Style Weighment" | Bug | Lable change | Leo | 2021-03-27 | Completed | Pass
118 | Sales | SO Creation | Product Details | Replace "Case wight" with "Case Weight" | Bug | UI | Leo | 2021-03-27 | Completed | Pass
119 | Sales | SO Creation | Header Search | Replace "Deliver" with "Delivery" | Bug | UI | Leo | 2021-03-27 | Completed | Pass
120 | Sales | SO Creation | Product details | Soacking Time (min) spelling mistake it should be "Soaking " 1.Variant code. 2.In information message also spelling mistake for variant | Bug | UI | Sandeep | 2021-04-06 | Completed | Pass | Uma
121 | Sales | SO Creation | Product details | In Product details column it is Pack style but in view it is pack type , should follow same column names. 1.Change Variant into Variant code. 2.Total cartons should be total cases | Bug | UI | Sandeep | 2021-04-06 | Completed | Pass | Uma
122 | Sales | So creation | Product Details | In pack style column weight is fixed?it is not allowed more than 100 | Bug | Validation | Sandeep | 2021-04-06 | Completed | Pass | Uma
123 | Sales | SO Creation | Sales order Tracker | In view form, the unit price has jumped to the nearest interger, I have given $4.61, Its showing $5 in the view form | Bug | Validation | Hemanth | 2021-04-07 | Completed | Pass | Uma |  | need to discuss with uma
124 | Sales | Sale order tracker | Detail view | In sale order view 1.Rename Process details title to " Certifications " 2.Rename PO Details title to " Packaging details " | Bug | UI | Sandeep | 2021-04-09 | Completed | Pass | Niveditha
125 | Sales | Sale order tracker | Sale order tracker | Click on sale order edit icon showing alert as erp.schemaxtch.in. says | Bug | UI | Sandeep | 2021-04-09 | Completed | Pass | Niveditha |  | Fixed but need to get tested
126 | Sales | So Creation | Product Deatils | Decemal values should not allow for pack style, glazzing, decimal values | Bug | Validation | Sandeep | 2021-04-19 | Completed | Pass | Niveditha
127 | Masters | Sales | Shipping term | Shipping term form name should be Shipping Term | Bug | UI |  |  | Completed | Pass | Dheeraj
128 | Sales | Sale order tracker | So View | Sorting feature missing |  | UI | Sandeep |  | Completed | Pass | Manisha
129 | Masters | Global | Customers | In custmer details view Currency is showing wrong | Bug | Functional | Sandeep | 2021-04-15 | Completed | Pass | Dheeraj
130 | Masters | Global | Payment terms | Unable to add payment term details getting error as ER_BAD_FIELD_ERROR: Unknown column 'PaymentTerms.payment_terms_category' in 'field list' | Bug | Sql Error | Sowjanya | 2021-04-14 | Completed | Pass | Niveditha
131 | Masters | Global | Packing methods | Showing "ER_BAD_FIELD_ERROR: Unknown column 'PaymentTerms.payment_terms_category' in 'field list'" | Bug | Sql Error | Sandeep | 2021-04-14 | Completed | Pass | Dheeraj
132 | Masters | Sales | SO process types | Unable to add SO process type details getting error as ER_NO_DEFAULT_FOR_FIELD: Field 'created_user' doesn't have a default value | Bug | Sql Error | Sowjanya | 2021-04-14 | Completed | Reopen | Niveditha
133 | Masters | Global | Taxes | in update validation missing , tax name and percentage accepts duplicates | Bug | Validation | Swathi | 2021-04-14 | Completed | Pass | Niveditha
134 | Masters | Global | Taxes | in taxes form change the input type of Tax% so that it will allow zero's | Bug | Validation | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
135 | Masters | Procurement | Vendors price list | View button is missing in Vendors price list | Bug | Functional | Sowjanya | 2021-04-15 | Completed | Pass | Karun Karthik
136 | Masters | Procurement | Sizes | Unable to add sizes getting error as ER_NO_DEFAULT_FOR_FIELD: Field 'created_user' doesn't have a default value | Bug | Sql Error | Sowjanya | 2021-04-15 | Completed | Pass | Dileep
137 | Masters | Procurement | Vendors | Give proper validation message for mandatory fields and also provide * symbol for mandotary fileds | Bug | Validation | Sandeep | 2021-04-19 | Completed | Pass | Karun Karthik
138 | Masters | Procurement | GRN Rejection Reasons | Rejection Reason code is not showing in View page | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass | Niveditha
139 | Masters | Procurement | Sizes | Form is showing 2 times | Bug | UI | Sandeep | 2021-04-21 | Completed | Pass | Dheeraj
140 | Masters | Warehouse | Levels | Enter space abr and click on submit levels are created Both ceate and update | Bug | Validation | Sandeep | 2021-04-21 | Completed | Pass | Karun Karthik
141 | Masters | Warehouse | Pallets | Unable to Deactivate | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass | Karun Karthik
142 | Masters | Warehouse | Zones | Enter space abr and click on submit levels are created Both ceate and update | Bug | Validation | Sandeep | 2021-04-21 | Completed | Pass | Karun Karthik
143 | Masters | Warehouse | Warehouse Master | Change the menu name as Warehouse masters into Warehouse | Bug | UI | Sandeep | 2021-04-21 | Completed | Pass | Niveditha
144 | Masters | Procurement | Vendors |  | Bug | Validation | Sandeep | 2021-04-08 | Completed | Open | lakshmi
145 | Masters | Procurement | Vendors price list | Unable to view the vendors price list details | Bug | Functional | Sowjanya | 2021-04-14 | Completed | Open | lakshmi
146 | Masters | Procurement | GRN Rejection Reasons | Provide * For Remarks text filed | Bug | UI | Sandeep | 2021-04-21 | Completed | Pass | Dileep
147 | Masters | Procurement | Sizes | Unable to add sizes getting error as ER_NO_DEFAULT_FOR_FIELD: Field 'created_user' doesn't have a default value | Bug | Sql Error | Sowjanya | 2021-04-14 | Completed | Pass | Dileep
148 | Masters | Global | Tax | Tax % Zero Not updated | Bug | Validation | Sandeep | 2021-04-14 | Completed | Open | Niveditha |  | Accepting but not displaying 0
149 | Masters | Procurement | ITEMS | Item category is not updated in ITEMS | Bug | Functional | Sowjanya | 2021-04-14 | Completed | Pass | Swathi
150 | Masters | Procurement | ITEMS | Submit functionality is not working | Bug | Functional | Sowjanya | 2021-04-14 | Completed | Open | Rohit
151 | Masters | Procurement | Vendors price list | Unable view vendors price list | Bug | Functional | Sandeep | 2021-04-14 | Completed | Open | Dheeraj |  | No grid view, This component only contains a card without the code for grid view
152 | Masters | Global | Departments | while updating duplicate department showing (ER_DUP_ENTRY: Duplicate entry 'CUTTING11' for key 'IDX_8a367b88085d359eb2fc3f4d2e') instead of this show the sweet alert | Bug | Sql Error | Swathi | 2021-04-14 | Completed | Pass | Dheeraj
153 | Masters | Procurement | Items | Item category displays wrong in items | Bug | Functional | Sowjanya | 2021-04-15 | Completed | Open | Karun Karthik |  | It is displaying item category correctly in items
154 | Masters | Procurement | Vendors price list | Need to add Total Vendors Price List, Active, Inactive status in Create page | Bug | Functional | Sowjanya | 2021-04-15 | Completed | Open | Dileep |  | No grid view, This component only contains a card without the code for grid view
155 | Masters | Procurement | Vendors price list | In Active/Deactive Vendors Price List pop message displays wrong | Bug | UI | Sowjanya | 2021-04-15 | Completed | Pass | Dileep
156 | Masters | Sales | Destination | Display Country name in grid view | Suggesition | UI | RK | 2021-04-19 | Completed | Open | Dileep
157 | Masters | Procurement | Vendors | Unable to add Vendors Showing "ER_TRUNCATED_WRONG_VALUE_FOR_FIELD: Incorrect integer value: 'EURO' for column 'currency_id' at row 1" | Bug | Functional | Sandeep | 2021-04-19 | Completed | Pass | Dileep
158 | Packaging | PO | Po | Can only add 2 variants of products per single form, the page blanks post 3rd one creation | Bug | Functional | Sowjanya | 2021-04-07 | Completed | Pass | Suraj
159 | Packaging | Store Issues | Store consumption | 1. Unable to add store consumption form getting error as Request failed with status code 500 | Bug | UI | Sowjanya | 2021-04-07 | Completed | Pass | Manisha | 2021-04-27
160 | Packaging | Store Return | Store return | 1. Sale order item dropdown is empty | Bug | Functional | Sowjanya | 2021-04-07 | Completed | Pass | Lakshimi
161 | Packaging | Po | Create Purchase Order | Total cost should not allow negative values | Bug | Validation | Sandeep | 2021-04-08 | Completed | Pass | Suraj
162 | Packaging | Po | Item Details | 1.Discount shuold be less than 100 , 2.Discount amount and tax amount should not be editble 3.Discount amount and tax amount should not be editble 4. Duplicate records rows created while update 5.Total cost is not showing in bottom of the page | Bug | Validation | Sandeep | 2021-04-08 | Completed | Pass | Lakshmi
163 | Packaging | BOM Calculation | BOM Calculation | Sale order dropdown is empty | Bug | Functional | Sowjanya | 2021-04-14 | Completed | Pass | Rohit
164 | Packaging | BOM calculation | BOM Details | Cilck on SO Number showing blank page | Bug | Functional | Sandeep | 2021-04-15 | Completed | Pass
165 | Packaging | Po | Po | Click on Po Showing error"ER_BAD_FIELD_ERROR: Unknown column 'PoCreation.exchange_rate' in 'field list' | Bug | Sql Error | Sandeep | 2021-04-17 | Completed | Pass | lakshmi
166 | Packaging | GRN Return | GRN return | Unable to add GRN Return details getting error as Request failed with status code 404 | Bug | Sql Error | Sowjanya | 2021-04-17 | Open | Open
167 | Packaging | Store Return | Store return | Unable to add Store Return details getting error as Request failed with status code 404 | Bug | Sql Error | Sowjanya | 2021-04-17 | Completed | Pass | Manisha
168 | Packaging | BOM Calculation | Packaging | BOM Calculation is showing "ER_WRONG_FIELD_WITH_GROUP: Expression #1 of SELECT list is not in GROUP BY clause and contains nonaggregated column 'erp_sales.BomDetails.item_category_id' which is not functionally dependent on columns in GROUP BY clause; this is incompatible with sql_mode=only_full_group_by" | Bug | Sql Error | Sandeep | 2021-04-19 | Completed | Pass | Ramya
169 | Sales | SO Creation | Customer Details | The final destination has gone into Numbers, check regarding the same | Bug | Sql Error | Hemanth | 2021-04-07 | Completed | Pass | Uma
170 | Sales | Sale order tracker | Sales order Tracker | SO tracker once opened, does not show End Customer Details and Destination Address | Bug | Functional | Leo | 2021-04-07 | Completed | Pass | Uma |  | No data in masters need to discvuss with RK
171 | Sales | So creation | Product details | 1.There is 6 Active variant codes but So creation form it is showing 12 2. There is 2 UOMs are active but So creation form it is showing 4 3.There is only 1 certification is active but So creation it is showing 2 | Bug | Functional | Sandeep | 2021-04-08 | Completed | Open | Uma |  | point no 2 and 3 are not required as they are not coming from masters
172 | Sales | SO creation | SO detail view | Total Weight and Total Amount shows " 08750.00020000.000" and "039968.25680001" | Bug | Validation | Leo | 2021-04-09 | Completed | Pass | Manisha
173 | Sales | So creation | Product details | Unable to add new sizes while select category is Skewers . | Bug | Functional | Sandeep | 2021-04-14 | Completed | Open | Uma |  | Hold by client
174 | Sales | Sale order tracker | Sale orders | In sale orders form getting error as ER_WRONG_FIELD_WITH_GROUP: Expression #1 of SELECT list is not in GROUP BY clause and contains nonaggregated column 'erp_sales.BomDetails.item_category_id' which is not functionally dependent on columns in GROUP BY clause; this is incompatible with sql_mode=only_full_group_by | Bug | Sql Error | Sowjanya | 2021-04-15 | Completed | Pass | RK
175 | Sales | So Creation | Product details | Pack style calculation showing wrong | Bug | Functional | Sandeep | 2021-04-17 | Completed | Pass | Uma
176 | Sales | So Creation | Product details | Case weight is showing Undefined in product details | Bug | Functional | Sandeep | 2021-04-17 | Completed | Pass | Uma
177 | Sales | So Creation | Product details | In Masters UOM are saved in Upper case but UOM drop down is showing lower case in productdetails | Bug | Functional | Sandeep | 2021-04-17 | Not Required | Reopen | Uma |  | UOM dropdown data in SO is not getting from masters
178 | Sales | So Creation | So Creation | Fill all the fields and click on submit showing "ER_NO_DEFAULT_FOR_FIELD: Field 'final_percentage' doesn't have a default value" | Bug | Validation | Sandeep | 2021-04-17 | Completed | Pass | Uma
179 | Sales | Sale order tracker | Sale order tracker | Ui is not good data overlapped | Bug | UI | Sandeep | 2021-04-17 | Completed | Pass | Manisha
180 | Sales | Sale order tracker | SO detail view | Certification data is showing wrong | Bug | Functional | Sandeep | 2021-04-17 | Completed | Pass | Manisha
181 | Sales | So Creation | Product Deatils | skewers varity sizes not showing for new size without refreshinhg page | Bug | Functional | Sandeep | 2021-04-19 | Completed | Pass | Uma
182 | Sales | So Creation | Product Deatils | Edit not working showing blank page | Bug | Functional | Sandeep | 2021-04-20 | Completed | Pass | Uma
183 | Sales | So Creation | Product Deatils | Net drained should be readonly | Bug | UI | Sandeep | 2021-04-20 | Completed | Pass | Uma
184 | Sales | Sale order tracker | SO Detail View | Product details not showing in product details and update also | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass | Manisha
185 | Sales | Sale order tracker | Sale order tracker | Select date range and click on get details grid view is not good | Bug | UI | Sandeep | 2021-04-21 | Completed | Pass | Manisha
186 | Sales | Sale order tracker | Sale order Detail View | Change the Item details name into product details | Bug | UI | Sandeep | 2021-04-21 | Completed | Pass | Manisha
187 | Sales | Sale order tracker | Sale order update | Update the product details and click on submit there is no responce | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass
188 | Packaging | BOM Calculation | BOM Calculation | Unable to add item category, item sizes and quantity and update also | Bug | Functional | Sandeep | 2021-04-21 | Completed | Open
189 | Sales | Sale order tracker | Sale order tracker | Total weight is showing wrong, total amount is not showing | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass | Manisha
190 | Sales | Sale order tracker | Sale order Detail View | ETA and ETD dates showing wrong | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass | Manisha
191 | Sales | SO Creation | Sale order form | Click on edit showing "text.toFixed is not a function" | Bug | Sql error | Sandeep | 2021-04-21 | Completed | Pass | Uma
192 | Sales | Sale order tracker | Sale order Detail View | Click on sale order number in grid view product details and ETA and ETD dates showing wrong | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass | Manisha
193 | Sales | Sale order tracker | Sale order Detail View | Certifications also showing wrong | Bug | Functional | Sandeep | 2021-04-21 | Completed | Pass | Manisha
194 | Sales | Sale order tracker | Sale order tracker | Date range not working | Bug | Validation | Sandeep | 2021-04-21 | Completed | Pass | Manisha
195 | Packaging | BOM Calculation | BOM Calculation | ITEM dropdown is empty | Bug | Functional | Sowjanya | 2021-04-14 | Completed | Open |  |  | 7y
196 | Masters | Global | Departments | In edit department please change heading as department | Bug | Lable change | Ravi | 2021-04-22 | Completed | Pass | Dileep
197 | Masters | Global | Departments | Department Name mandatory field showing alert 'deptName' is required need to show department name is required | Bug | Lable change | Ravi | 2021-04-22 | Completed | Pass | Dileep
198 | Masters | Global | Taxes | Without enter any details click on submit UI Changed | Bug | UI | Ravi | 2021-04-22 | Completed | Pass | Dileep
199 | Masters | Global | Currencies | While sorting with currency name then short is not working | Bug | Functional | Ravi | 2021-04-22 | Completed | Re open | dileep
200 | Masters | Global | Payment Modes | While sorting with payment mode then short is not working | Bug | Functional | Ravi | 2021-04-22 | Completed | Pass | dileep
201 | Masters | Global | Payment Modes | In View Payment Modes change label as Payment Mode now showing Mode in small letters | Bug | Lable change | Ravi | 2021-04-22 | Completed | Pass | Dileep
202 | Masters | Global | UOMs | In view UOMs sorting is not working | Bug | Functional | Ravi | 2021-04-22 | Completed | Pass | Dileep
203 | Sales | Sale order tracker | Sale order tracker | In edit case weight is showing Undeifiend | Bug | Functional | Sandeep | 2021-04-22 | Completed | Pass | Uma
204 | Sales | Sale order tracker | Detail view | Change the ETA and ETD | Bug | UI | Sandeep | 2021-04-22 | Completed | Pass | Manisha
205 | Masters | Global | Employees | In create employee, the field employee role need to provide dropdown | Suggestion | UI | Ravi | 2021-04-22 | Completed | Open | Dheeraj
206 | Sales | So Creation | SO Creation | Soaking time is following the same time as the previous product if not edited in the new product | Bug | Functional | Leo | 2021-04-22 | Completed | Open
207 | Sales | So Creation | SO Creation | Lab Inspection's are not necessary to create a sales order. Unrestrict sale order to be created even if no LAB inspection inputs are given, But should be able to edit that option later too | Bug | Functional | Leo | 2021-04-22 | Completed | Open
208 | Sales | Sale order tracker | Sale Order Tracker | Load type shows MIXED if the product is more than 2, it should show if product is more than 1. | Bug | Functional | Leo | 2021-04-22 | Completed | Open
209 | Sales | Sale order tracker | Sale Order Tracker | Super Confusing UI for the Sale order Tracker | Bug | UI | Leo | 2021-04-22 | Completed | Open
210 | Sales | Sale order tracker | Sale Order Tracker | If Sale Order is Edited "Action" then the default date changes to 02-03-2021 for all orders | Bug | Functional | Leo | 2021-04-22 | Completed | Open
211 | Masters | Global | Countries | Country name sorting is not working | Bug | Functional | Ravi | 2021-04-22 | Completed | Pass | Dileep
212 | Masters | Global | Certificates | Certification name sorting is not working | Bug | Functional | Sandeep | 2021-04-22 | Completed | Pass | Dheeraj
213 | Masters | Global | Packing Methods | sorting is not working |  | Functional | Ravi | 2021-04-22 | Completed | Pass | Dheeraj
214 | Masters | Global | Customers | In customers form mobile number accepting more than 10 numbers | Bug | Validation | Ravi | 2021-04-22 | Completed | Re open | Dheeraj |  | Need to discuss with Rk
215 | Masters | Global | Delivery Terms | Delivery Term name sorting is not working | Bug | Functional | Sandeep | 2021-04-22 | Completed | Pass | Dheeraj
216 | Masters | Global | Shipping Terms | Shipment Term Name sorting is not working properly | Bug | Functional | Ravi | 2021-04-22 | Completed | Pass | Dheeraj
217 | Sales | Sale order tracker | Sale order tracker | Alignment is not good for Get details and Reset button | Bug | UI | Sandeep | 2021-04-23 | Completed | Open | Manisha
218 | Sales | Sale order tracker | Sale order tracker | Provide mandatory symbol for * ETA and ETD and | Bug | Validation | Sandeep | 2021-04-23 | Not Required | Open | Manisha |  | ETA & ETD are not mandatory
219 | Sales | Sale order tracker | Sale order Detail View | Download button functionality not working | Bug | Functional | Sandeep | 2021-04-23 | Completed | Open | Manisha
220 | Masters | Procurement | Vendors price list | Lable name should be Tax % into Tax Percentage % and also change in grid view | Bug | Lable change | Sandeep | 2021-04-23 | Completed | Open | Ramya
221 | Masters | Procurement | Vendors price list | Should not edit if vendors price list is inactive | Bug | Validation | Sandeep | 2021-04-23 | Completed | Open | Ramya
222 | Masters | Procurement | Vendors price list | Data is not showing while click on View button | Bug | Functional | Sandeep | 2021-04-23 | Completed | Open | Ramya
223 | Masters | Packaging | Bom Calculation | In Bom Calculation getting error as Request failed with status code 500 | Bug | Sql error | Sowjanya | 2021-04-23 | Completed | Open | Lakshmi
224 | Masters | Sales | Products | Without entering remarks form not saved getting error ER_NO_DEFAULT_FOR_FIELD: Field 'remarks' doesn't have a default value | Bug | Validation | Ravi | 2021-04-23 | Completed | Open | Dheeraj
225 | Masters | Sales | Products | In View Products sorting is not working | Bug | Functional | Ravi | 2021-04-23 | Completed | Pass | Dheeraj
226 | Masters | Sales | SO Types | while sorting with sale order type blank page is displayed | Bug | Functional | Ravi | 2021-04-23 | Completed | Re open | Dileep
227 | Masters | Sales | So Process Type | Without entering remarks form not saved getting error ER_NO_DEFAULT_FOR_FIELD: Field 'remarks' doesn't have a default value | Bug | Validation | Ravi | 2021-04-23 | Not Required | Open | Dileep
228 | Masters | Sales | So Process Type | Process Type Code sorting is not working | Bug | Functional | Ravi | 2021-04-23 | Completed | Re open | Karun Karthik |  | Sorting is done based on lenght, now changed it to alphanumeric.
229 | Masters | Sales | Food Type | in view change label type of food to food type | Bug | Lable change | Ravi | 2021-04-23 | Completed | Pass | Karun Karthik
230 | Masters | Sales | Val Addn1 | While sorting with name blank page displayed | Bug | Functional | Ravi | 2021-04-23 | Completed | Pass | Dheeraj
231 | Masters | Sales | Val Addn2 | in view sorting is not working | Bug | Functional | Ravi | 2021-04-23 | Completed | Re open | Dheeraj
232 | Masters | Sales | Val Addn1 | Need to show status column i.e Active or In-Active | Bug | Functional | Ravi | 2021-04-23 | Completed | Pass | Rohith
233 | Masters | Sales | Val Addn2 | Need to show status column i.e Active or In-Active | Bug | Functional | Ravi | 2021-04-23 | Completed | Pass | Rohith
234 | Masters | Sales | Val Addn3 | Need to show status column i.e Active or In-Active | Bug | Functional | Ravi | 2021-04-23 | Completed | Pass | Rohith
235 | Masters | Sales | Val Addn4 | in view sorting is not working | Bug | Functional | Ravi | 2021-04-23 | Completed | pass | Dheeraj
236 | Masters | Procurement | Item category | Need to show Item Category code in Grid View | Bug | UI | Sowjanya | 2021-04-23 | Completed | Re open | Dileep
237 | Masters | Procurement | Item category | Change the menu name as Item Categories instead of Item categories | Bug | UI | Sowjanya | 2021-04-23 | Completed | Pass | Dheeraj
238 | Masters | Procurement | Item category | While sorting with Remarks blank page displayed | Bug | Functional | Sowjanya | 2021-04-23 | Completed | Pass | Dheeraj
239 | Masters | Procurement | Items | Alignment issues of Item category and item name in Create Form | Bug | UI | Sowjanya | 2021-04-23 | Completed | Re open | Kartheek
240 | Masters | Procurement | Items | Alignment issues of Item category, item name and product code in Updation Form | Bug | UI | Sowjanya | 2021-04-23 | Completed | Re open | Kartheek
241 | Masters | Procurement | Items | While sorting with Remarks blank page displayed | Bug | UI | Sowjanya | 2021-04-23 | Completed | Pass | Dheeraj
242 | Masters | Procurement | Vendors | Provide Validation for contact number, GST number, Postal code | Bug | Validation | Sowjanya | 2021-04-23 | Completed | Re open | Dileep
243 | Masters | Procurement | Vendors Price List | Vendors price list data is not showing in vendors price list view form | Bug | Functional | Sowjanya | 2021-04-23 | Completed | Open | Kartheek |  | vendor price list grid is blank and not coded.
244 | Masters | Procurement | Sizes | Change the menu name as Sizes instead of SIZES | Bug | UI | Sowjanya | 2021-04-23 | Completed | Re open | Dheeraj
245 | Masters | Sales | Destination | Need to show country name in grid view | Bug | UI | Ravi | 2021-04-23 | Completed | Open | Rohith
246 | Masters | Sales | Destination | Need to provide sorting in grid view | Bug | Functional | Ravi | 2021-04-23 | Completed | Pass | Dheeraj
247 | Masters | Sales | End customer | In view, currency sorting is not working | Bug | Functional | Sandeep | 2021-04-23 | Completed | Open | Rohith
248 | Masters | Sales | End customer | In update, delete brand and again add brand and click on submit at that time getting this error ER_BAD_NULL_ERROR: Column 'end_customer_id' cannot be null | Bug | Functional | Ravi | 2021-04-23 | Open | Open | Kartheek |  | While deleting brand, the end_customer_id is also deleted. Backend logic should be checked.
249 | Masters | Sales | Roles | Total Roles Should be left alignment | Bug | UI | Sowjanya | 2021-04-23 | Completed | Re open | Kartheek
250 | Masters | Sales | Roles | In Role name Search is not working | Bug | UI | Sowjanya | 2021-04-23 | Completed | Re open | Kartheek
251 | Masters | Sales | SKU code | While editing any sku code showing wrong data and some fields showing numbers in dropdown | Bug | Functional | Ravi | 2021-04-23 | Completed | Open | Dileep
252 | Masters | Sales | SKU code | without entering any data click on submit need to change validation messages it is showing for example 'foodTypeId' is required for all fields showing like their respective ids | Bug | UI | Ravi | 2021-04-23 | Completed | Open | Dheeraj
253 | Masters | Sales | Roles | Duplicates are allowed in Roles | Bug | UI | Sowjanya | 2021-04-23 | Completed | Open | Divya
254 | Masters | Procurement | Item category | in edit item category elements alignment is missing | Bug | UI | Ravi | 2021-04-23 | Completed | Open | Dileep
255 | Masters | Procurement | Item category | while clicking on edit its in deactive, it shows message you can't edit deactivated employee but need to show you can't edit deactivated item category | Bug | Lable change | Sandeep | 2021-04-23 | Completed | Pass | Rohith
256 | Masters | Procurement | Items | In grid view change the order item category need to show first then item name | Bug | UI | Sandeep | 2021-04-23 | Completed | Open | Kartheek
257 | Masters | Procurement | Items | in grid view item name search(click on search icon) searching is not working | Bug | Functional | Ravi | 2021-04-23 | Completed | Open | Rohith
258 | Masters | Procurement | Vendors | while clicking on price list of deactive vendor, in vendor name dropdown it is showing number | Bug | Functional | Ravi | 2021-04-23 | Completed | Open | Kartheek
259 | Masters | Procurement | Vendors | in grid view Country,Currency search(click on search icon) searching is not working | Bug | Functional | Ravi | 2021-04-23 | Completed | Re open | Dileep
260 | Masters | Procurement | GRN Rejection Reasons | in edit Reason elements alignment is missing | Bug | UI | Ravi | 2021-04-23 | Completed | Open | Dileep
261 | Masters | Procurement | Sizes | Size name sorting is not working | Bug | Functional | Ravi | 2021-04-23 | Completed | Pass | Rohith
262 | Masters | Global | Departments | deactivated department edit is showing message You Cannot Edit Deactivated Item -Variant but need to show you cannot edit deactivated departments | Bug | Lable change | Sandeep | 2021-04-23 | Completed | Re open | Kartheek
263 | Masters | Global | Taxes | deactivated taxes edit is showing message You Cannot Edit Deactivated Item -Variant but need to show you cannot edit deactivated taxes | Bug | Lable change | Ravi | 2021-04-23 | Completed | Re open | Kartheek
264 | Masters | Global | Currencies | deactivated currencies edit is showing message You Cannot Edit Deactivated Item -Variant but need to show you cannot edit deactivated currencies | Bug | Lable change | Ravi | 2021-04-23 | Completed | Re open | Kartheek
265 | Masters | Global | Customers | deactivated customer edit need to show alert message you cannot edit deactivated customer | Bug | Lable change | Ravi | 2021-04-23 | Completed | Re open | Dileep
266 | Masters | Sales | So Process Type | deactivated process type edit is showing message You Cannot Edit Deactivated saleorderprocessType change it as you cannot edit deactivated sale order process type | Bug | Lable change | Ravi | 2021-04-23 | Completed | Pass | Dileep
267 | Masters | Sales | Val Addn1 | deactivated val addn1 edit is showing message You Cannot Edit Deactivated Type1 Data need to show you cannot edit deactivated value | Bug | Lable change | Ravi | 2021-04-23 | Completed | Pass | Dheeraj
268 | Masters | Sales | Val Addn2 | deactivated val addn2 edit is showing message You Cannot Edit Deactivated Types of value addition 2 need to show you cannot edit deactivated value | Bug | Lable change | Ravi | 2021-04-23 | Completed | Pass | Dheeraj
269 | Masters | Sales | Val Addn3 | deactivated val addn3 edit is showing message You Cannot Edit Deactivated Types of value addition 2 need to show you cannot edit deactivated value | Bug | Lable change | Ravi | 2021-04-23 | Completed | Pass | Dheeraj
270 | Masters | Sales | SKU Code | deactivated sku code edit is showing message You Cannot Edit Deactivated code but need to show you cannot edit deactivated SKU Code | Bug | Lable change | Ravi | 2021-04-23 | Completed | Re open | Dheeraj
271 | Sales | SO Creation | SO Creation | in so creation without entering ETD it show Missing EDL date need to show Missing ETD date,Currency shows Missing currenct need to show missing currency,delivery terms showing Missing delivaery terms | Bug | Lable change | Sandeep | 2021-04-23 | Completed | Pass | Uma
272 | Masters | Global | Customers | without entering any details click on submit then enter details customers form is not working after entering the mobile number also it is showing enter valid mobile number and click on submit it cannot perform any action | Bug | Functional | Ravi | 2021-04-23 | Completed | Re open | Dileep
273 | Packaging | BOM Calculation | BOM Calculation | Total gird UI is shrinked | Bug | UI | Ravi | 2021-04-24 | Completed | Pass | Manisha
274 | Packaging | BOM Calculation | BOM Calculation | while editing bom calculation in that edit item details there item showing id | Bug | Functional | Ravi | 2021-04-24 | Completed | Pass | Ramya
275 | Packaging | BOM Calculation | BOM Calculation | while editing bom calculation in that edit item details available quantity and required quantity are not showing | Bug | Functional | Ravi | 2021-04-24 | Completed | Pass | Ramya
276 | Masters | Warehouse | Levels | in level update form remove view button | Bug | UI | Ravi | 2021-04-24 | Completed | Pass | Nageswar
277 | Masters | Warehouse | Levels | When i create levels click on submit 3 times same level saved 3 times | Bug | Validation | Ravi | 2021-04-24 | Completed | Pass | Nageswar
278 | Masters | Warehouse | Levels | in update level it is showing label as add level | Bug | Lable change | Ravi | 2021-04-24 | Completed | Pass | Nageswar
279 | Masters | Warehouse | Pallets | in create form heading is pallet methods change it as pallets | Bug | Lable change | Sandeep | 2021-04-24 | Completed | Pass | Nageswar
280 | Masters | Warehouse | Pallets | in pallets update form remove view button | Bug | UI | Sandeep | 2021-04-24 | Completed | Pass | Nageswar
281 | Masters | Warehouse | Pallets | When i create pallets click on submit 3 times same Pallet saved 3 times | Bug | Validation | Sandeep | 2021-04-24 | Completed | Pass | Nageswar
282 | Masters | Warehouse | Zones | in zones update form remove view button | Bug | UI | Ravi | 2021-04-24 | Completed | Re open | Dileep
283 | Masters | Warehouse | Zones | in update zone it is showing label as add zone | Bug | Lable change | Ravi | 2021-04-24 | Completed | Re open | Dileep
284 | Masters | Warehouse | Racks | In add racks form align ment issues are there | Bug | UI | Ravi | 2021-04-24 | Completed | Pass | Niveditha
285 | Masters | Warehouse | Racks | in update Racks it is showing label as add Racks | Bug | Lable change | Ravi | 2021-04-24 | Completed | Open | Niveditha
286 | Masters | Warehouse | Racks | in racks update form remove view button and alignment issue | Bug | UI | Ravi | 2021-04-24 | Completed | Open | Divya
287 | Masters | Warehouse | Racks | after creating racks in grid view zone name is not displayed it is showing empty | Bug | Functional | Ravi | 2021-04-24 | Completed | Open | Divya
288 | Masters | Warehouse | Racks | click on edit there zone name showing id and rack code is not displayed | Bug | Functional | Ravi | 2021-04-24 | Completed | Open | Divya
289 | Masters | Warehouse | Racks | without entering any data click on submit it is showing zone id required but need to show zone name is required | Bug | Lable change | Ravi | 2021-04-24 | Completed | open | Niveditha
290 | Masters | Warehouse | Racks | in grid view displaying data wrongly in rack code column displaying rack name | Bug | Functional | Ravi | 2021-04-24 | Completed | open | Niveditha
291 | Masters | Warehouse | Racks | when we do sorting in grid view it displaying blank page | Bug | Functional | Ravi | 2021-04-24 | Completed | Open | Divya
292 | Masters | Warehouse | Racks | If in a zone an existing rack is created in the form it is accepting | Bug | Functional | Divya | 2021-04-24 | Open | Open | Divya
293 | Masters | Warehouse | Locations | Getting error Request failed with status code 404 | Bug | Sql error | Sandeep | 2021-04-24 | Completed | Open | Nageswar
294 | Masters | Warehouse | Rack Endcoustomer Mapping | Getting error Request failed with status code 404 | Bug | Sql error | Sandeep | 2021-04-24 | Completed | Open | Nageswar
295 | Masters | Warehouse | Rack Endcoustomer Mapping | change menu name to Rack Endcustomer Mapping instead of Rack-Endcustomer-Mapping | Bug | Lable change | Sandeep | 2021-04-24 | Completed | Open | Nageswar
296 | Sales | Sale order tracker | Sale order tracker | in sale order tracker in grid view click on + symbol in sale order items showing more empty columns | Bug | UI | Ravi | 2021-04-24 | Completed | Open | Manisha
297 | Masters | Global | Departments | without giving department name just giving space and click on submit the form saved same in update also | Bug | Validation | Ravi | 2021-04-24 | Completed | Open | Dileep
298 | Masters | Global | Taxes | without entering tax name just giving space and click on submit the form saved | Bug | Validation | Ravi | 2021-04-24 | Completed | Open | Dileep
299 | Masters | Global | Taxes | enter same tax name again showing error like ER_DUP_ENTRY: Duplicate entry 'IGST' for key 'IDX_cf6b5f5566cd59ed1ef4668fc5' | Bug | Sql error | Ravi | 2021-04-24 | Completed | Open | Dheeraj
300 | Masters | Global | Countries | Country name allowing duplicate values i.e same name created multiple times | Bug | Validation | Ravi | 2021-04-24 | Completed | Open | Divya
301 | Masters | Sales | SO Types | enter same so type name showing error like ER_DUP_ENTRY: Duplicate entry 'Direct Sale' for key 'IDX_60b976078f0e85297c20d8911b' | Bug | Sql error | Ravi | 2021-04-24 | Completed | Open | Divya
302 | Masters | Sales | Brands | Brand name allowing duplicate values | Bug | Validation | Ravi | 2021-04-24 | Completed | Open | Dheeraj
303 | Masters | Procurement | GRN Rejection Reasons | Rejection reason code is not showing mandatory but without entering reason code and save the form it shows error ER_NO_DEFAULT_FOR_FIELD: Field 'rejection_reason_code' doesn't have a default value | Bug | Validation | Ravi | 2021-04-24 | Completed | open | Niveditha
304 | Masters | Global | Global | For All Screens in mandatory fields enter space and click on submit form saved but we have restirct | Bug | Validation | Ravi | 2021-04-24 | Completed | Open | Rohith
305 | Masters | Sales | Sales | For All Screens in mandatory fields enter space and click on submit form saved but we have restirct | Bug | Validation | Ravi | 2021-04-24 | Completed | Open | Rohith
306 | Masters | Procurement | Procurement | For All Screens in mandatory fields enter space and click on submit form saved but we have restirct | Bug | Validation | Ravi | 2021-04-24 | Completed | Open | Niveditha
307 | Sales | Sale order tracker | Sale order tracker | when we click on sale order no in that there is option download and click on that it is redirected to http://206.189.138.212/erpx/null | Bug | Functional | Ravi | 2021-04-24 | Completed | Open | Manisha
308 | Packaging | PO | PO | In PO view Search is not working | Bug | UI | Sowjanya | 2021-04-26 | Completed | Open | Suraj
309 | Packaging | PO | PO | While sorting with SO number, expected delivery date blank page displayed | Bug | UI | Sowjanya | 2021-04-26 | Completed | Re open | Suraj
310 | Packaging | PO | PO | Unable to add PO details getting error as Request failed with status code 500 | Bug | Sql error | Sowjanya | 2021-04-26 | Completed | Pass | Suraj
311 | Packaging | GRN | GRN | While sorting with GRN number blank page displayed | Bug | UI | Sowjanya | 2021-04-26 | Completed | Pass | Uma
312 | Packaging | GRN | GRN | Unable to add GRN details getting error as ER_BAD_FIELD_ERROR: Unknown column 'NaN' in 'field list' | Bug | Sql error | Sowjanya | 2021-04-26 | Completed | Pass | Uma
313 | Packaging | GRN Return | GRN Return | Unable to add GRN return details getting error as Request failed with status code 404 | Bug | Sql error | Sowjanya | 2021-04-26 | Open | Open | Dheeraj
314 | Packaging | Store Issues | Store Issues | Unable to add Store issues getting error as Request failed with status code 500 | Bug | Sql error | Sowjanya | 2021-04-26 | Completed | Pass | Manisha | 2021-04-27
315 | Packaging | Store Return | Store Return | Unable to add Store Return details getting error as Request failed with status code 404 | Bug | Sql error | Sowjanya | 2021-04-26 | Completed | Pass | Manisha
316 | Sales | SO Creation | SO Creation | System taking same product multiple times with same data but we can add only once | Bug | Functional | Ravi | 2021-04-26 | Completed | Pass | Uma | 2021-04-29
317 | Sales | SO Creation | SO Creation | Without entering the net drain weight, case weight is calculated but as per formula after entering net drain weight we can calculate case weight, calculation wrong | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Uma
318 | Sales | SO Creation | SO Creation | when we adding multiple products some time when we enter pack style, the calculation of case weight,net weight,net amount will be calculated | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Uma
319 | Sales | SO Creation | SO Creation | when we enter grade min 10 and max 1 it is showing alert but when we add product it is added | Bug | Validation | Ravi | 2021-04-26 | Completed | Pass | Uma | 2021-04-29
320 | Sales | SO Creation | SO Creation | when we enter glazing min 10 and max 1 it is not showing any alert | Bug | Validation | Ravi |  | Completed | Pass | Uma | 2021-04-29
321 | Sales | SO Creation | SO Creation | in variant code showing in active variant codes also dont show inactive variant codes and also showing first value is empty | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Uma
322 | Sales | SO Creation | SO Creation | after submit so creation it will not redirect any where and also not reloaded because of this i can submit multiple times in so tracker it is showing multiple times(ex: clicking submit 6 times in so it is showing 6 times) | Bug | Functional | Ravi | 2021-04-26 | Completed | Pass | Uma
323 | Sales | Sale order tracker | Sale order tracker | when we click to see sale order items after total amount column more no of empty columns are showing | Bug | UI | Ravi | 2021-04-26 | Completed | Open | Manisha
324 | Sales | Sale order tracker | Sale order tracker | when we click on so number detailed view opend but ui mismatching when compared with form i.e elements order | Bug | UI | Ravi | 2021-04-26 | Completed | Open | Manisha
325 | Sales | Sale order tracker | Sale order tracker | when we click on so number detailed view opend and there total pouches are showing wrong as per form my total pouches are 1050 in detailed view showing total pouches 210 | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Manisha |  | Need Clarity
326 | Sales | Sale order tracker | So Creation | when i click on edit its redirecting to so and after done some changes click on submit it is showing so created successfully but need to show so updated successfully | Bug | Lable change | Ravi | 2021-04-26 | Completed | Open | Uma
327 | Sales | Sale order tracker | Sale order tracker | in sale order detail view QA/QC Inspection is not showing | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Manisha
328 | Sales | SO Creation | SO Creation | in update so when i enter lab inspection and QA/QC inspection details form not updating but in network it is showing response success but when again edit in lab and qa/qc inspection chek boxes are not checked. | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Uma | 2021-05-04
329 | Packaging | PO | PO | Transportation field allows negative values | Bug | Validation | Ravi | 2021-04-26 | Completed | Pass | Ramya
330 | Packaging | BOM Calculation | BOM Calculation | in bom calculation for particular SO edit item details showing wrong category and item name showing id | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Ramya
331 | Packaging | BOM Calculation | BOM Calculation | when we update an item then item category is not saving | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Ramya
332 | Packaging | BOM Calculation | BOM Calculation | Showing wrong items data in bom calculation edit | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Ramya
333 | Packaging | Store Issues | Store Issues | In Create form Item category dropdown data displays wrong | Bug | Functional | Sowjanya | 2021-04-26 | Completed | Open | Manisha | 2021-04-27
334 | Packaging | GRN | GRN | in GRN Edit GRN Date and Invoic dates are changed and GRN items are not showing | Bug | Functional | Ravi | 2021-04-26 | Not Required | Open | Uma |  | GRN update is on hold
335 | Packaging | GRN | GRN | in GRN Edit without updating the accepted qty click on submit GRN Created, if we can update accepted qty then click on submit GRN Not Created | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Uma
336 | Packaging | Store Issues | Store Issues | without enter any details and click on submit form redirected to view | Bug | Functional | Ravi | 2021-04-26 | Completed | Open | Manisha
337 | Packaging | Store Issues | Store Issues | item name showing item id is required and consumed quantity is showing quantity is required need to change as item name is required and consumed quantity is required | Bug | Lable change | Ravi | 2021-04-26 | Completed | Open | Rohith
338 | Packaging | Store Issues | Store Issues | increase the width of sale order dropdown why because unable to see full Sale Order Number | Bug | UI | Ravi | 2021-04-26 | Completed | Open | Manisha | 2021-04-27
339 | Packaging | GRN | GRN | total cost not updating | Bug | Functional | RK | 2021-04-25 | Completed | Open | Uma
340 | Packaging | GRN | GRN | accepted quantity should auto fill as received quantity | Bug | UI | RK | 2021-04-25 | Completed | Open | Uma
341 | Packaging | GRN | GRN | disable the button once user clicks on submit and redirect the page, otherwise multiple times stock is adding | Bug | UI | RK | 2021-04-25 | Completed | Open | Uma
342 | Packaging | GRN | GRN | Once receive all the items in PO close the respective PO | Bug | Functional | RK | 2021-04-25 | Completed | Open | Uma
343 | Packaging | GRN | GRN | based on so id if item id is existed update the stock otherwise insert the stock row | Bug | Functional | RK | 2021-04-25 | Completed | Open | Uma
344 | Sales | SO Creation | SO Creation | ETD date accepting Previous dates compared to current date | Bug | Validation | Ravi | 2021-04-27 | Completed | Pass | Uma
345 | Sales | SO Creation | SO Creation | without adding products click on submit button then button got disabled. and now add products still submit button not enabled | Bug | Functional | Ravi | 2021-04-27 | Completed | Open | Uma
346 | Sales | SO Creation | SO Creation | whithout adding product details and click on submit so created. | Bug | Functional | Ravi | 2021-04-27 | Completed | Open | Uma
347 | Sales | SO Creation | SO Creation | First i selected category ring, after entering the products changed category to skewers and again changed to ring, then added products are removed | Bug | Functional | Ravi | 2021-04-27 | Not Required | Open | Uma |  | as it will be moved to item categories in next phase
348 | Sales | SO Creation | SO Creation | when i select category skewers it is showing button new size when i add size from SO Creation form it is redirecting to sizes view | Bug | Functional | Ravi | 2021-04-27 | Completed | Open | Uma
349 | Sales | SO Creation | SO Creation | when i edit product and click on reset button then again click on edit it is not edited | Bug | Functional | Ravi | 2021-04-27 | Completed | Open | Uma
350 | Packaging | BOM Calculation | BOM Calculation | in bom calculation edit, when i edit particular item order quantity it is showing enter valid item quantity and click on update it is not saving | Bug | Functional | Ravi | 2021-04-27 | Completed | Open | Ramya
351 | Packaging | PO | PO | expected delivery date accepting previous dates compared to purchase order date | Bug | Validation | Ravi | 2021-04-27 | Completed | Pass | Ramya
352 | Packaging | PO | PO | while creating so seleted currency is INR but in po it is showing as USD | Bug | Functional | Ravi | 2021-04-27 | Completed | Open | Ramya |  | It is vendor based currency
353 | Packaging | PO | PO | when we click on submit in both create and update, the tax amounts are changed (ex:before submit tax amount is 510, after submit it is 2) | Bug | Functional | Ravi | 2021-04-27 | Completed | Open | Ramya
354 | Packaging | GRN | GRN | invoice date accepting previous dates compared to grn date | Bug | Validation | Ravi | 2021-04-27 | Completed | Open | Uma
355 | Packaging | GRN | GRN | in edit GRN po number showing id and form not saved | Bug | Functional | Ravi | 2021-04-27 | Not Required | Open | Uma |  | GRN update is on hold
356 | Packaging | GRN | GRN | Trnsportation amount missing in form | Bug | Functional | RK | 2021-04-28 | Completed | Open | Uma
357 | Packaging | GRN | GRN Details | In GRN Details approver lable change as Approver | Bug | Lable change | Sandeep | 2021-04-28 | Completed | Open | Uma | 2021-04-29
358 | Sales | SO Creation | Product details | Provide mandatory fileds for packin style and glazzing ,leave the textfields are empty and click on add products are not added | Bug | Validation | Sandeep | 2021-04-29 | Completed | Open | Uma | 2021-04-29
359 | Sales | Sale order tracker | So Details view | Change the lable name as Packing details to Packing Details | Bug | Lable change | Sandeep | 2021-04-29 | Completed | Open | Manisha | 2021-04-30
360 | Sales | Sale order tracker | So Details view | change the lable name as Is barnd Approved? insted of Brand Design Approved | Bug | Lable change | Sandeep | 2021-04-29 | Completed | Open | Manisha | 2021-04-30
361 | Sales | Sale order tracker | So Details view | In So creation , brand type and Is barnd approved drop downs data is showing captail letters but in So tracker details view showing small letters | Bug | Lable change | Sandeep | 2021-04-29 | Completed | Open | Manisha | 2021-04-30
362 | Sales | Sale order tracker | So Details view | Open the So details form and refresh the page showing Data not found | Bug | Functional | Sandeep | 2021-04-29 | Completed | Open | Manisha | 2021-05-04
363 | Packaging | BOM Calculation | BOM Calculation | Form name should be Unique | Bug | Lable change | Sandeep | 2021-04-29 | Not Required | Open | Ramya
364 | Packaging | BOM Calculation | BOM Calculation | Size, Avalible quantity and requried quantity is showing NaN | Bug | Functional | Sandeep | 2021-04-29 | Completed | Open | Ramya
365 | Packaging | BOM Calculation | BOM Calculation | While update the item details Action buttons are missing | Bug | Functional | Sandeep | 2021-04-29 | Completed | Open | Ramya
366 | Masters | Sales | Products | without enter remarks and submit form getting error ER_NO_DEFAULT_FOR_FIELD: Field 'remarks' doesn't have a default value | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Karthik
367 | Masters | Global | Taxes | In update with out any changes and click on submit it is showing Already exits | Bug | Functional | Sandeep | 2021-04-29 | Completed | Open | Dheeraj
368 | Masters | Sales | Products | if we hover the mouse on any column in grid view UI is shrinking | Bug | UI | Ravi | 2021-04-29 | Completed | Open | Karthik
369 | Masters | Sales | SO types | Search is not working in sale order type | Bug | UI | Sowjanya | 2021-04-29 | Completed | Open | Karthik
370 | Masters | Procurement | Item Category | Item Category code search is not working | Bug | UI | Sowjanya | 2021-04-29 | Completed | Open | Dheeraj
371 | Masters | Procurement | Item Category | In edit item category elements alignment is missing | Bug | UI | Sowjanya | 2021-04-29 | Completed | Open | Dheeraj
372 | Masters | Procurement | Item Category | Change the lable name as Item Category Code instead of ItemCategory Code in Grid View | Bug | UI | Sowjanya | 2021-04-29 | Completed | Open | Dheeraj
373 | Masters | Sales | So Process Type | only enter mandatory fields and click on submit getting this error ER_NO_DEFAULT_FOR_FIELD: Field 'name' doesn't have a default value | Bug | Functional | Ravi | 2021-04-29 | Not Required | Open | Karthik
374 | Masters | Global | Taxes | In Update while giving same tax name ER_DUP_ENTRY: Duplicate entry 'GST' for key 'IDX_cf6b5f5566cd59ed1ef4668fc5' | Bug | Sql error | Sandeep | 2021-04-29 | Completed | Open | Dheeraj
375 | Masters | Global | Payment Modes | Unable to create payment modes | Bug | Functional | Sandeep | 2021-04-29 | Completed | Open | Dileep
376 | Masters | Procurement | GRN Rejection Reasons | In edit item GRN rejection reasons alignment is missing | Bug | UI | Sowjanya | 2021-04-29 | Completed | Open | Dheeraj
377 | Sales | Sale order tracker | Sale order tracker | when we click on so tracker menu getting this error ER_BAD_FIELD_ERROR: Unknown column 'saleOrderItemsInfo.dispatched_qty' in 'field list' | Bug | Sql error | Ravi | 2021-04-29 | Completed | Open | Manisha | 2021-04-29
378 | Masters | Procurement | GRN Rejection Reasons | Rejection reason search is not working in Grid view | Bug | UI | Sowjanya | 2021-04-29 | Completed | Open | Dheeraj
379 | Sales | SO Creation | SO Creation | when we create so getting this error Cannot read property 'finalPercentage' of undefined | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Uma | 2021-04-29
380 | Sales | SO Creation | SO Creation | when we update SO, if we add products there Pack Style,Case Weight,Net Weight,Unit Price,Net Amount are not showing decimal values | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Uma | 2021-05-04
381 | Sales | SO Creation | SO Creation | when we update SO, if we add products there soaking style showing differently | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Uma | 2021-05-04
382 | Sales | SO Creation | SO Creation | In edit SO if we are adding any product then click on submit getting error form not updated | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Uma | 2021-05-05
383 | Sales | Sale order tracker | Sale order tracker | when we create so, in sale order tracker it is showing at the middle | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Manisha |  | tracker showing based on aging(ETD)
384 | Packaging | BOM Calculation | BOM Calculation | when i click on submit on bom calculation form need to redirect to view. | Bug | Redirection | Ravi | 2021-04-29 | Completed | Open | Ramya
385 | Packaging | PO | PO | when we click on PO menu then getting this error ER_BAD_FIELD_ERROR: Unknown column 'PoCreation.po_type' in 'field list' | Bug | Sql error | Ravi | 2021-04-29 | Completed | Open | Ramya
386 | Packaging | PO | PO | when i create PO by default PO Type is WITH SO, because i select so number and vendor click on submit it is showing PO Type is required | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Ramya
387 | Packaging | PO | PO | PO create with so then getting this error this.soService.getAllBomDetailsForSoIdInPo is not a function | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Ramya
388 | Packaging | PO | PO | when i select without SO and enter all details click on submit it is showing Sale Order is Required | Bug | Functional | Ravi | 2021-04-29 | Completed | Open | Ramya
389 | Packaging | Store Return | Store Return | Whiile sorting with store return date blank page is displayed | Bug | Functional | Sowjanya | 2021-04-29 | Completed | Open | Manisha | 2021-04-29
390 | Packaging | Store Return | Store Return | Search is not working in Store Return Grid | Bug | Functional | Sowjanya | 2021-04-29 | Completed | Open | Manisha | 2021-04-29
391 | Packaging | Stock | Stock | Unable to add stock details getting error as Request failed with status code 500 | Bug | Functional | Sowjanya | 2021-04-29 | Open | Open
392 | Packaging | GRN return | GRN return | Unable to create GRN Item details getting error as ER_NO_REFERENCED_ROW_2: Cannot add or update a child row: a foreign key constraint fails (`erpx_dev_procurement`.`grn_item_returns`, CONSTRAINT `FK_9edcf4573b5719563f64d43917d` FOREIGN KEY (`grn_id`) REFERENCES `grn` (`grn_id`) ON DELETE NO ACTION ON UPDATE NO ACTION) | Bug | Sql error | Sowjanya | 2021-04-29 | Open | Open | Dheeraj
393 | Packaging | GRN return | GRN return | In GRN return form getting error as Request failed with status code 404 | Bug | Sql error | Sowjanya | 2021-04-29 | Open | Open | Dheeraj
394 | Masters | Global | Employees | Give popup messge while Active and deactive | Bug | Validation | Sandeep | 2021-04-29 | Completed | Open | Niveditha
395 | Masters | Global | Customers | Give popup messge while Active and deactive | Bug | Validation | Sandeep | 2021-04-29 | Completed | Open | Niveditha
396 | Masters | Global | Customers | Inactive payments modes showing in Customers payment mode drop down | Bug | Functional | Sandeep | 2021-04-29 | Completed | Open | Niveditha
397 | Masters | Global | Countries | Country name should be Unique | Bug | Validation | Sandeep | 2021-04-29 | Completed | Open | Dheeraj
398 | Masters | Global | Payment Terms | UI is not good in Update form | Bug | UI | Sandeep | 2021-04-29 | Completed | Open | Niveditha
399 | Sales | SO Creation | SO Creation | Vendor category type is not showing in So Creation Payment type drop down | Bug | Functional | Sandeep | 2021-04-29 | Not Required | Open | Uma |  | Showing only customer type payment terms in dropdown
400 | Masters | Warehouse | Racks | Unable to Rack details getting error as ER_NO_DEFAULT_FOR_FIELD: Field 'rack_code' doesn't have a default value | Bug | Sql error | Sowjanya | 2021-04-29 | Open | Open | Divya
401 | Packaging | PO | PO | while Create PO without SO, while adding PO items button shown as UPDATE | Bug | UI | Ravi | 2021-04-30 | Completed | Open | Ramya
402 | Packaging | PO | PO | Click on view button showing "Failed To Get Po Info" | Bug | Functional | Sandeep | 2021-04-30 | Completed | Open | Ramya |  | Build issue
403 | Packaging | PO | Create Po without So | Deactive payment terms is showing in Payment terms drop down | Bug | Functional | Sandeep | 2021-04-30 | Completed | Open | Ramya
404 | Packaging | PO | PO | in po items change lable Tax(%) to TaxPercentage(%) | Bug | Lable change | Sandeep | 2021-04-30 | Completed | Open | Ramya
405 | Packaging | PO | PO items form | Deactivated tax % is showing | Bug | Functional | Sandeep | 2021-04-30 | Completed | Open | Ramya
406 | Packaging | PO | PO | Deactivated vendors are showing in vendors drop down | Bug | Functional | Sandeep | 2021-04-30 | Completed | Open | Ramya |  | Build issue
407 | Sales | SO Creation | SO Creation | when we select category Skewers while adding new size remove view button in that form because it is redirecting to sizes grid | Bug | Functional | Ravi | 2021-04-30 | Hold | Open | Uma |  | As it was the masters form,removal of view button als effected in masters
408 | Sales | SO Creation | SO Creation | when we add new size in popup, then reload the so creation form then only that size displayed in skewer variety | Bug | Functional | Ravi | 2021-04-30 | Completed | Open | Uma |  | It was working fine
409 | Sales | Sale order tracker | Sale order tracker | when we click on so tracker menu getting this error ER_BAD_FIELD_ERROR: Unknown column 'saleOrderItemsInfo.dispatched_qty' in 'field list' | Bug | Sql error | Ravi | 2021-04-30 | Completed | Open | Manisha | 2021-04-30 | build issue
410 | Sales | SO Creation | SO Creation | in so creation soaking style having 0% in sku codes but so created successfully | Bug | Functional | Ravi | 2021-04-30 | Completed | Open | Uma |  | As it was having 0 % final percentage will save as 0
411 | Packaging | PO | PO | while Create PO without SO, while adding PO items button shown as UPDATE need to show ADD | Bug | UI | Ravi | 2021-05-03 | Completed | Open | Ramya
412 | Packaging | PO | PO | while create PO without SO adding item details can take same item multiple times with same data but we need to restrict | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
413 | Packaging | PO | PO | after adding items if i delete one item the total amount not changed accordingly | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
414 | Packaging | PO | PO | while editing PO tax amount in item details changed to 2 (ex: while creating PO tax amount is 4.75 after submit it changed as 2) | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
415 | Packaging | PO | PO | in details view showing wrong tax amount against item | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
416 | Packaging | PO | PO | while edit PO total cost is showing wrong | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
417 | Packaging | PO | PO | need to show total amount,currency,delivery address in detail view | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
418 | Sales | SO Creation | SO Creation | In SO edit when i delete one product click on submit agin showing same product | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Uma | 2021-05-04
419 | Packaging | PO | PO | Exchange rate should not accept negative values | Bug | Validation | Sandeep | 2021-05-03 | Completed | Open | Ramya
420 | Packaging | PO | PO | Quantity is showing NaN | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Ramya
421 | Packaging | PO | PO | Unable to create Po , it is showing Cannot read property 'status' of undefined | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Ramya
422 | Packaging | PO | PO | while edit PO the PO Type showing WITH SO but actually it is Without SO | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
423 | Packaging | PO | PO | while edit PO when we click on submit it is showing PO Type is required but it is in readonly mode | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
424 | Packaging | GRN Return | GRN Return | Return quantity is not accepting values. | Bug | Functional | Sandeep | 2021-05-03 | Open | Open | Harish
425 | Packaging | PO | PO | when we create PO without SO click on submit multiple time then Multiple PO's generated with Same data | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Ramya
426 | Packaging | Store Return | Store Return | Click on view button it is showing blank page | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Ramya
427 | Packaging | PO | PO | While Create PO with SO,Currency is not showing against vendor | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Ramya
428 | Packaging | PO | PO | Select Po type is with SO and select So No and select vendors and click on submit showing "Items Price List Not Updated For Selected Vendor" But it is showing in Without SO | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Ramya
429 | Packaging | GRN | GRN | while creating GRN update any item details, tax amount changed to 0 | Bug | Functional | Ravi | 2021-05-03 | Not Required | Open | Uma | 2021-05-04 | As fetching data from PO .It is calculating based on those values
430 | Packaging | GRN | GRN | GRN Items Tax Percentage and Tax Amount Showing Wrong | Bug | Functional | Sandeep | 2021-05-03 | Not Required | Open | Uma | 2021-05-04 | As fetching data from PO .It is calculating based on those values
431 | Packaging | GRN | GRN | if i have two items in grn but update one item and click on submit GRN Created and now i want to update 2nd item in that particular PO, that is not showing in dropdown. | Bug | Functional | Ravi | 2021-05-03 | Not Required | Open | Uma | 2021-05-05 | It's working fine
432 | Packaging | GRN | GRN | in grn grid view change date format of grn date and invoice date | Bug | UI | Ravi | 2021-05-03 | Completed | Open | Suraj
433 | Packaging | GRN | GRN | In detailed view show po number and change date format and UI missing | Bug | UI | Ravi | 2021-05-03 | Completed | Open | Suraj
434 | Packaging | BOM Calculation | BOM Calculation | in edit item size showing N/A but in textbox it is showing 11 | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Ramya
435 | Masters | Procurement | Items | In Add items Item details are mandatory but in update validatiopn is missing | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Dileep |  | item name is not mandatory "packing material" item category for other categories its mandatory
436 | Masters | Procurement | Items | in update size is drop down selected as Small and click on update but it is showing NA | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Dileep
437 | Masters | Sales | Products | HSN code not displayed in Grid view | Bug | Complete | Sandeep | 2021-05-03 | Completed | Open | Dileep
438 | Masters | Sales | Products | HSN code not displayed in Edit form | Bug | Complete | Sandeep | 2021-05-03 | Completed | Open | Dileep
439 | Sales | SO Creation | SO Creation | when i select category skewers and add sizes then sizes are not reflecting without refresh when clicking on ok button in the modal instead of close button | Bug | Functional | Ravi | 2021-05-03 | Completed | Open | Uma | 2021-05-04
439 | Masters | Sales | So Process Type | enter sale order process type and clickon submit showing ER_NO_DEFAULT_FOR_FIELD: Field 'name' doesn't have a default value | Bug | Functional | Sandeep | 2021-05-03 | Not Required | Open
440 | Masters | Sales | Food Type | Sorting functionality is missing | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Dileep
441 | Masters | Sales | Val Addn1 | showing alert message type1 data created successfully change it as value addition1 created successfully | Bug | Lable change | Sandeep | 2021-05-03 | Completed | Open | Dileep
442 | Masters | Sales | Val Addn4 | showing alert message product created successfully change it as value addition4 created successfully | Bug | Lable change | Sandeep | 2021-05-03 | Completed | Open | Dileep
443 | Masters | Sales | SKU Code | Sorting functionality is missing | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Nageswar
444 | Masters | Sales | Brands | Action functionality missing | Bug | Functional | Sandeep | 2021-05-03 | Completed | Open | Nageswar
445 | Masters | Warehouse | Racks | Inactive Zones are showing in Zone name drop down | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Nageswar
446 | Masters | Warehouse | Racks | Unable to create Racks showing "Cannot read property 'zoneId' of undefined" | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Nageswar
447 | Logistics | Commercials Invoice | Commercials Invoice | Change menu name from common invoice to Commercials Invoice | Bug | Lable change | Ravi | 2021-05-04 | Open | Open
448 | Logistics | Commercials Invoice | Commercials Invoice | Change the print heading to commercials invoice | Bug | Lable change | Ravi | 2021-05-04 | Open | Open
449 | Logistics | Commercials Invoice | Commercials Invoice | headings to be in bold | Bug | UI | Ravi | 2021-05-04 | Open | Open
450 | Masters | Warehouse | Locations | Active Levels are not displayed | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Nageswar
451 | Masters | Warehouse | Columns | Columns code and column No is not showing in grid view | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Nageswar
452 | Masters | Warehouse | Columns | Action button missing while deactive | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Nageswar
453 | Sales | SO Creation | SO Creation | while edit SO it is showing error Cannot read property 'split' of null and showing blank page | Bug | Functional | Ravi | 2021-05-04 | Completed | Open | Uma
454 | Masters | Warehouse | Rack EndCustomer mapping | Click on Rack EndCustomer mapping showing Request failed with status code 404 | Bug | Sql error | Sandeep | 2021-05-04 | Open | Open
455 | Sales | SO Creation | SO Creation | in SO edit delivery terms showing id | Bug | Functional | Ravi | 2021-05-04 | Hold | Open | Uma |  | Need more time for getting all items service in update
456 | Logistics | Commercials Invoice | Commercials Invoice | in consignee,importer on record change address format and show FDA Registration No in next line | Bug | UI | Ravi | 2021-05-04 | Open | Open
457 | Logistics | Commercials Invoice | Commercials Invoice | Port of discharge and final destination make it bold | Bug | UI | Ravi | 2021-05-04 | Open | Open
458 | Logistics | Commercials Invoice | Commercials Invoice | All Amounts and numbers should be right align | Bug | UI | Ravi | 2021-05-04 | Open | Open
459 | Masters | Warehouse | Rack EndCustomer mapping | Total Rack End custoemrs is missing | Bug | UI | Sandeep | 2021-05-04 | Completed | Open | Nageswar
460 | Logistics | Commercials Invoice | Commercials Invoice | total amount in dollars is not showing amount but in words it is showing | Bug | Functional | Ravi | 2021-05-04 | Open | Open
461 | Logistics | Customer Invoice | Customer Invoice | Change heading from Cus invoice to Customer Invoice | Bug | Lable change | Ravi | 2021-05-04 | Open | Open
462 | Logistics | Customer Invoice | Customer Invoice | container No,liner seal No,bill of lading no showing empty | Bug | Functional | Ravi | 2021-05-04 | Open | Open
463 | Logistics | Customer Invoice | Customer Invoice | Amounts and numbers should be right align | Bug | UI | Ravi | 2021-05-04 | Open | Open
464 | Logistics | Customer Invoice | Customer Invoice | Currency (USD) showing like this 113,975.00 0.00 0.00 0.00 0.00 | Bug | Functional | Ravi | 2021-05-04 | Open | Open
465 | Logistics | Customer Invoice | Customer Invoice | Showing wrong data against the headings | Bug | Functional | Ravi | 2021-05-04 | Open | Open
466 | Logistics | Commercials Invoice | Commercials Invoice | when we click on print button it is not working | Bug | Functional | Ravi | 2021-05-04 | Open | Open
467 | Logistics | Customer Invoice | Customer Invoice | when we click on print button it is not working | Bug | Functional | Ravi | 2021-05-04 | Open | Open
468 | Logistics | Plant Packing List | Plant Packing List | container No,liner seal No,bill of lading no showing empty | Bug | Functional | Ravi | 2021-05-04 | Open | Open | Dheeraj
469 | Logistics | Plant Packing List | Plant Packing List | Quantity in kgs net weight coloum all the values alignment missing | Bug | UI | Ravi | 2021-05-04 | Open | Open | Dheeraj
470 | Logistics | Plant Packing List | Plant Packing List | when we click on print button it is not working | Bug | UI | Ravi | 2021-05-04 | Open | Open | Dheeraj
471 | Logistics | Plant Packing List | Plant Packing List | All Amounts and numbers should be right align | Bug | UI | Ravi | 2021-05-04 | Open | Open | Dheeraj
472 | Logistics | Commercials Packing List | Commercials Packing List | Change heading from common packing list to commercials packing list | Bug | Lable change | Ravi | 2021-05-04 | Completed | Open | Karthik
473 | Logistics | Commercials Packing List | Commercials Packing List | Amounts and numbers should be right align | Bug | UI | Ravi | 2021-05-04 | Completed | Open | Karthik
474 | Logistics | Commercials Packing List | Commercials Packing List | Total net wt, Total gross Wt showing #Ref | Bug | Functional | Ravi | 2021-05-04 | Completed | Open | Karthik
475 | Logistics | Commercials Packing List | Commercials Packing List | when we click on print button it is not working | Bug | Functional | Ravi | 2021-05-04 | Open | Open | Dheeraj
476 | Logistics | Shipping Instructions | Shipping Instructions | when we click on print button it is not working | Bug | Functional | Ravi | 2021-05-04 | Open | Open | Karthik
477 | Logistics | Shipping Instructions | Shipping Instructions | incomplete requirement | Bug | Functional | Ravi | 2021-05-04 | Open | Open | Karthik
478 | Sales | SO Creation | SO Creation | when i select category skewers then skewers and skewer variaty are mandatory | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Uma | 2021-05-04
479 | Sales | SO Creation | SO Creation | when i add product with category skewers then skewer and skewer variaty need to show in grid | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Uma | 2021-05-04
480 | Sales | SO Creation | SO Creation | when i enter min grade 1 and max grade 1 system accepting but we need to restrict | Bug | Functional | Ravi | 2021-05-04 | Completed | Open | Uma | 2021-05-04
481 | Sales | SO Creation | SO Creation | when i select category skewer i unable to add same product with different skewer variaty | Bug | Functional | Ravi | 2021-05-04 | Completed | Open | Uma | 2021-05-04
482 | Sales | SO Creation | SO Creation | while adding the product i am not given skewers and skewer variaty but edit that product it is showing skewers and skewer variaty | Bug | Functional | Ravi | 2021-05-04 | Not Required | Open | Uma | 2021-05-04 | As making skewers and skewer variety as madatory
483 | Sales | SO Creation | SO Creation | when i enter min glazing 1 and max glazing 1 system accepting but we need to restrict | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Uma | 2021-05-04
484 | Sales | SO Creation | SO Creation | when i create SO i checked surveyar loading and click on submit then in edit it is showing unchecked | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Uma
485 | Sales | SO Creation | SO Creation | when i create SO Selected category skewers but when i edit particular SO skewers and skewer variaty are not showing in form | Bug | Functional | Ravi | 2021-05-04 | Completed | Open | Uma | 2021-05-05
486 | Logistics | Container Register | Container Register | Showing balnk page while click on Sale order No and Container Number sorting | Bug | Functional | Sandeep | 2021-05-04 | Completed | Open | Rohit
487 | Packaging | PO | PO | increase the width of sale order dropdown why because unable to see full Sale Order Number | Bug | UI | Ravi | 2021-05-04 | Completed | Open | Ramya
488 | Logistics | Container Register | Container Register | Change the lable name as Ready to book to Ready To Book | Bug | UI | Sandeep | 2021-05-04 | Completed | Open | Rohit
489 | Logistics | Container Register | Container Register | Change the lable name as Dispatched to plant to Dispatched to Plant | Bug | UI | Sandeep | 2021-05-05 | Completed | Open | Rohit
490 | Logistics | Container Register | Container Register | Status is not changed but click on Book a slot it is showing Container Booked Successfully | Bug | Functional | Sandeep | 2021-05-05 | Open | Open
491 | Logistics | Bill of Ladding | Bill of Lading | Sorting functionality is not working for sale order No, container number showing blank page | Bug | Functional | Sandeep | 2021-05-05 | Open | Open
492 | Logistics | Bill of Ladding | Bill of Lading | Click on SET TO DRAFT showing Request failed with status code 500 | Bug | Functional | Sandeep | 2021-05-05 | Open | Open
493 | Logistics | Invoices | Invoices | Clickon Invoice menu showing Cannot read property 'endCustomerCode' of undefined | Bug | Sql error | Sandeep | 2021-05-05 | Open | Open
494 | Packaging | BOM Calculation | BOM Calculation | when i deactivate item in BOM Tracker edit but still in BOM Details it is showing in OPEN need to show inactive or cancelled | Bug | Functional | Ravi | 2021-05-05 | Open | Open | Manisha
495 | Packaging | PO | PO | By default PO Type is with so then i select Vendor and click on submit it is showing PO Type is required | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Ramya
496 | Packaging | PO | PO | without entering mandatory fields and click on submit then button disabled | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Ramya
497 | Packaging | PO | PO | tax amount showing 9.7e+2 | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Ramya
498 | Packaging | BOM Calculation | BOM Calculation | In BOM Tracker after GRN not showing any status | Bug | Functional | Ravi | 2021-05-05 | Open | Open | Manisha
499 | Packaging | Stock | Stock | after GRN Stock is not showing | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Suraj
500 | Packaging | PO | PO | If i have 3 items in BOM Tracker but in po it is showing only 2 items | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Ramya
501 | Packaging | PO | PO | Initially tax amount showing correctly if i update any thing against item then tax amout changed and showing with special characters | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Ramya
502 | Packaging | PO | PO | Total amount and total cost are showing different | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Ramya
503 | Logistics | Invoices | Invoices | Unit price hould not Accept negative values | Bug | Validation | Sandeep | 2021-05-05 | Completed | Open |  | 2021-05-07
504 | Logistics | Invoices | Invoices | Exchange rate should not accept negative values | Bug | Validation | Sandeep | 2021-05-05 | Completed | Open |  | 2021-05-07
505 | Logistics | Invoices | Invoices | In saleorder there are 3 items but in Invoice it is showing 2 items | Bug | Functional | Sandeep | 2021-05-05 | Open | Open
506 | Logistics | Invoices | Invoices | Change the lable name as currency to Currency | Bug | Lable change | Sandeep | 2021-05-05 | Completed | Open |  | 2021-05-07
507 | Packaging | PO | PO | Unable to Edit PO Item details | Bug | Functional | Sandeep | 2021-05-05 | Completed | Open | Ramya
507 | Packaging | BOM Calculation | BOM Calculation | Change the lable name as Grn quantity to GRN Quantity | Bug | Lable change | Sandeep | 2021-05-05 | Open | Open
508 | Packaging | PO | PO | In Create PO Tax Percentage is Mandtory but in ViewTaxpercentage is showing empty | Bug | Functional | Sandeep | 2021-05-05 | Completed | Open | Ramya
510 | Packaging | Store Issues | Store Issues | change 'saleOrderId' is required to Sale Order No is Required | Bug | Lable change | Sandeep | 2021-05-05 | Completed | Open | Manisha | 2021-05-06
511 | Packaging | Store Issues | Store Issues | Increase the width of sale order and indent date | Bug | UI | Sandeep | 2021-05-05 | Completed | Open | Manisha | 2021-05-06
512 | Packaging | Store Issues | Store Issues | for text box it is showing as Available Quantity and in grid it is showing available stock change it to available quantity | Bug | Lable change | Ravi | 2021-05-05 | Completed | Open | Manisha | 2021-05-06
513 | Packaging | Store Issues | Store Issues | when i add item i have available quantity but when i click on add button available quantity not showing in grid | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Manisha | 2021-05-06
514 | Packaging | Store Issues | Store Issues | when we click on store issues menu it is showing Request failed with status code 404 | Bug | Sql error | Ravi | 2021-05-05 | Completed | Open | Manisha | 2021-05-06
515 | Packaging | Store Issues | Store Issues | when i enter all details and click on submit it is showing error Request failed with status code 500 | Bug | Sql error | Ravi | 2021-05-05 | Completed | Open | Manisha | 2021-05-06
516 | Packaging | Store Issues | Store Issues | when i add item and then i delete that item then SUBMIT button got disabled | Bug | Functional | Ravi | 2021-05-05 | Completed | Open | Manisha | 2021-05-06
517 | Sales | SO Creation | SO Creation | SO Creation Category Issue In SO Creation while select category skeweres showing alert message. ![image](/uploads/a6af5a40424c7f72293e69fe53291ca1/image.png) | Bug | Validation | Ravi | 2021-07-05 | Completed | Open | Uma
518 | Sales | SO Creation | SO Creation | SO Creation Item Update Issue when we select category skewers and add some items, then edit one item change the skewer variaty and click on update getting this error. ![image](/uploads/7339458ffae749a358695dd1623b9a06/image.png) | Bug | Functional | Ravi | 2021-07-05 | Completed | Open | Uma
519 | Sales | Sale order tracker | SO Tracker | Steps: 1.Create SO with category skewers. 2.Go to SO Tracker. 3.Click on + symbol There in sale order items need to show skewers and skewer variaty. ![image](/uploads/5a6c1ca7a318afdda5e0abc09a1c0ea0/image.png) | Bug | Functional | Ravi | 2021-07-05 | Completed | Open | Manisha
520 | Sales | SO Creation | SO Creation | SO Update Issue Steps: 1.Create SO With Category Skewers. 2.Go to SO Tracker. 3.Click on edit. 4.Then go to product details skewer variaty showing id's in grid view. ![image](/uploads/cfa3df7ce443095cadbf44e237b62cfd/image.png) 5.Now Click on Submit then getting this error. ![image](/uploads/11ae7abf85f58737e31a723c0e8ba7e6/image.png) | Bug | Functional | Ravi | 2021-07-05 | Completed | Open | Uma
521 | Sales | Sale order tracker | SO Tracker | SO Tracker Button Issue Steps: 1.Create SO. 2.Go to SO Tracker. 3.Click on Open. ![image](/uploads/2498bb690ccef6c304bb58b86cb090fb/image.png) 4.Then getting this issue. ![image](/uploads/3215d1262ea5509b875ac14068a9ee22/image.png) | Bug | Functional | Ravi | 2021-07-05 | Open | Open | Manisha
522 | Packaging | BOM Tracker | BOM Tracker | Steps: 1.Create SO. 2.Go to BOM Tracker 3.There Need to change heading BOM Calculation to BOM Tracker ![image](/uploads/c1a4b31c9a61e72595bf82e8d32f27ae/image.png) 4.Change BOM Details to BOM Tracker. ![image](/uploads/f0138de24669a4420552a00f2a7c5444/image.png) | Bug | Label Change | Ravi | 2021-07-05 | Completed | Open | Ramya
523 | Packaging | PO | PO | PO Tax Amount Issue Steps: 1.Go to BOM Tracker. 2.Click on any OPEN SO. 3.edit particulat po item details. 4.Then check the tax amount. ![image](/uploads/eaae7e5c99d4ca378042735fde1fb5e6/image.png) 5.without update amounts and click on update its updated but those are required fields. ![image](/uploads/5664106c9fc8c4a790cc03b5e39c047b/image.png) | Bug | Functional | Ravi | 2021-07-05 | Open | Open | Ramya
524 | Packaging | PO | PO | PO Detailed View Issue 1.Go to PO. 2.Click on detailed view. 3.Tax(%) is not displayed. ![image](/uploads/bf3f9cfc5c238546a382b369445b6f21/image.png) 4.Need to show total amount also. | Bug | Functional | Sandeep | 2021-07-05 | Open | Open | Ramya
525 | Packaging | GRN | GRN | GRN Item Details Issue Steps: 1.Go to GRN. 2.Select PO and you can get item details. 3.Now update accepted quantity. ![image](/uploads/15ae3364e92a25ec9108588beda34692/image.png) 4.Now change accepted quantity and again enter same quantity then tax amount changed. ![image](/uploads/75b70eac46c71c9077060b24a6d89f6a/image.png) 5.In GRN grid view need to show PO Number. 6.In GRN Detailed View PO Number is missing. 7.Change GRN Date format. ![image](/uploads/15ab002826a585fc5a2e136632516d56/image.png) | Bug | Functional | Sandeep | 2021-07-05 | Open | Open | Ramya
526 | Packaging | GRN Return | GRN Return | GRN Return Blcoker 1.Click on GRN Return Menu Getting the issue. ![image](/uploads/ff97e30fc0b5afb0e7fa9cf1b0e5fc0c/image.png) 2.If we want to do GRN Return Form not showing GRN Numbers. ![image](/uploads/8539773674269f6b3f341da195322fdc/image.png) | Bug | Blocker | Ravi | 2021-07-05 | Open | Open | RK
527 | Packaging | Stock | Stock | Stock not showing any data. Steps: 1.Create GRN. 2.After GRN Stock need to show in stock menu. 3.Stock Not showing. ![image](/uploads/3625c23f21e1457069f1db34f54fb8f4/image.png) | Bug | Functional | Sandeep | 2021-07-05 | Open | Open | Manisha
528 | Sales | SO Creation | SO Creation | Change the label name as Delivery terms into Delivery Terms ![image](/uploads/fcab1e2309b55bff862ba1376f880b98/image.png) | Bug | Label Change | Sandeep | 2021-07-05 | Completed | Open | Uma
529 | Packaging | PO | PO | Unable to create PO Name drop down is not working in PO Item form. ![image](/uploads/32e1256e70b05a84cfa98585d81539ed/image.png) | Bug | Blocker | Sandeep | 2021-07-05 | Completed | Open | Ramya
530 | Packaging | PO | PO | Round off total Cost ![image](/uploads/d6f71ea1ee6b0cabe77e9dde928fe9ed/image.png) | Bug | Validation | Sandeep | 2021-07-05 | Completed | Open | Ramya
531 | Packaging | PO | PO | Edit functionality is not working. ![image](/uploads/c2716087aa94a31c5421c734a0d160e3/image.png) | Bug | Functional | Sandeep | 2021-07-05 | Completed | Open | Ramya
532 | Packaging | PO | PO | 1.Tax Percentage is not showing in PO View ![image](/uploads/fe9140d8a5194b011735e42b381bd09a/image.png) 2.Change the label in view form Tax % into Tax Percentage | Bug | Functional | Sandeep | 2021-07-05 | Completed | Open | Ramya
533 | Packaging | PO | PO | In PO item Tax(%) id saved because of that GRN Tax percentage and Tax amount got changed | Bug | Functional | Ravi | 2021-07-05 | Open | Open | Ramya

## crs
S.no | Date | Module | Sub Module | Feature | Dev status | Testing status | Assignee
1 | 2021-07-04 | sales | so creation | mandatory removal for inspection | completed |  | Uma
2 | 2021-07-04 | sales | so creation | shrimp size need to maintain for category Ring | completed |  | Uma
3 | 2021-07-04 | sales | so creation | No. of skewers need to be added in item details for packing materia BOM | completed |  | Uma
S.no | 2021-07-04 | sales | so creation | need to convert OZ price to LB as giving unitprice for lb irrespective of UOM and total weight should be in LB | completed |  | Uma
4 | 2021-08-04 | sales | so creation | Need to give option for entry of LOT number in inspection details | completed |  | Uma
5 | 2021-09-04 | sales | SO creation | category need to be added in product details | Hold for present |  | Uma
6 | 2021-10-04 | sales | SO creation | skewer variety need to be added in iproduct details to calculate the BOM | Cmpleted |  | Uma
S.no | 2021-10-04 | Masters | Items | need to map items and sizes with brand ,packing category,grade,varient,packing style to auto calculatethe BOM |  |  | Swathi&suraj
7 | 2021-10-04 | Sales | SO creation | need add logic for saving of bom calculation parameters from SO | Completed |  | Uma
8 | 2021-11-04 | Sales | SO creation | need to give editable shrimpsize option for FWFC and FWNC irrespective of category | Completed |  | Uma
9 | 14-04-2021 | Sales | SO creation | Payment terms need to select against customer | Completed |  | Uma
S.no | 2021-03-04 | Masters | Value edition 1,2,3 | Need Edit access and deactivation access too | Completed | Pass | Uma
10 | 2021-05-04 | Sales | SO Creation | If a Country is Selected, the Destination States should automatically be filtered from that selected country | Completed | Pass | Uma
11 | 2021-06-04 | Sales | SO Creation | Rename Process details title to " Certifications " | Completed | Pass | Uma
12 | 2021-06-04 | Sales | SO Creation | Rename PO Details title to " Packaging details " | Completed | Pass | Uma
S.no | 2021-06-04 | Sales | SO Creation | BAP should have a max of 4 stars only | Completed | Pass | Uma
13 | 2021-06-04 | Sales | SO Creation | Rename "ACS" certificate to "ASC" | Completed | Pass | Uma
14 | 2021-06-04 | Sales | Product Details | Grade limit needs to increase ( 300 ) | Completed | Pass | Uma
15 | 2021-06-04 | Sales | Sale Order Tracker | All the orders should automatically be sorted based on first ETD | Completed | Pass | Manisha
S.no | 2021-06-04 | Sales | Sale Order Tracker | Need a Filter of Orders based on UNIT's (Unit 1/2/ kakinada) | Completed | Pass | Manisha
16 | 2021-07-04 | Sales order Creation | Lab inspection | Please remove the (*) for Lab inspection, there might be orders without any inspection | Completed | Pass | Uma
17 | 2021-07-04 | Sales order Creation | Process deatils | For Item category " Ring, Need additioanl box for Shrimp Weight, that will be used for our BOM calculation, for example = 16 oz ring which has12 oz shrimp and 4 oz sauce- But price and packaging is done for 16. OZ | Completed | Pass | Uma
18 | 2021-07-04 | Sales | SO Creation | Need to add kakinada in units dropdown | Completed | Pass | Uma
S.no | 2021-07-04 | Sales | Sales Order tracker | Need an additional input to show 1 - Final Destination 2 - Type of product (Ring, Skewer, Pouch) 3 - Unit Assigned | Completed
19 | 2021-09-04 | So creation | Product details | Please change "shrimp size" to "Net drained Weight" and give edit option after when selected FWFC/FCNW in any category- Pouchs too- by giving filling | Open
20 | 20-04-2021 | So creation | Product details | Items should save from SO with respect to selected grade,brand,variety,pack style as size mapping not needed | Completed |  | Uma
21 | 20-04-2021 | Masters | Items | Items should maintain against brand,grade,packstyle, varient and UOM instead of varient,grade,packstyle,brand- size N/A for few items | Completed |  | Lakshmi
S.no | 25-04-2021 | Sales | SO Creation | need save master brand in BOM details instead of customer brand as different cutsomer having multiple brands | Completed |  | Uma
22 | 26-04-2021 | Packaging | GRN | need to update GRN received quantity in BOM feature | Completed |  | Uma
| 28-04-2021 | Packaging | PO | Need to give feature for raising PO for inventory irrespective of saleorder | In-Progress |  | Lakshmi
| 28-04-2021 | Packaging | BOM Tracker | Need to add a feature of assigning existing inventory to a saleorder(frontend) | In-Progress |  | lakshmi
| 28-04-2021 | Packaging | BOM Tracker | Need to add a logic for assign stock from inventory to saleorder(backend) | Completed |  | Uma
| 28-04-2021 | Sales | SO Creation | Need to a logic for required qty of BOM with respect to minimum stock and reserved stock | Completed |  | Uma
|  | Packaging | PO | Need to change form against vendor and sale order using Vendors price list | Completed |  | lakshmi
|  | Packaging | PO | Need to change form as with so and with out so as client requirement | Completed |  | lakshmi
| 2021-04-05 | Logistics | Invoice | Need to freight charges and remove discount and tax adding feature from Invoice | Completed |  | Uma
| 2021-04-05 | Sales | SO creation | remove all decimal values for weight quantities | Completed |  | Uma